## Sheet1
|  |  |  | A8RX-TECSAI-MDL-001 | [6 empty] | TEC/SAI MASTER DELIVERABLE LIST for FEED
STATUS REPORT 4-SEP-2020
CONTRACT # | DISCIPLINE # | DISCIPLINE | WBS | Document Number |  |  | TEC SAI Document Number | REVISION | Document Category A/B/C | Submittal purpouse IFA / IFI | Document Title | Due Date | Received Date | Transmittal IBTS # | WF # | WF # due date | Transmittal OBTS # | Submittal Date | Remarks
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-LST-001 | LST | 1 | 082623C-0000-NM-0051-0001 | 0 | B | IFA | BATTERY LIMITS INTERFACE TABLES AG AND UG | 2020-11-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PLN-001 | PLN | 1 | 082623C-0000-PLG-0102 | 0 | B | IFA | WBS | 2020-09-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-001 | PRC | 1 | 082623C-0000-PP-0101 | 0 | B | IFA | FEED EXECUTION PLAN | 2020-09-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-002 | PRC | 2 | 082623C-0000-PP-0126 | 0 | B | IFA | EPCC EXECUTION PLAN | 2021-03-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-003 | PRC | 3 | 082623C-0000-PP-0100 | 0 | B | IFA | PROJECT ORGANIZATION CHART | 2020-09-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-004 | PRC | 4 | 082623C-0000-PP-0110 | 0 | B | IFA | DOCUMENT ISSUE, DISTRIBUTION TO AND APPROVAL BY PKN/PMC | 2020-09-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-005 | PRC | 5 | 082623C-0000-PP-0301 | 0 | B | IFA | SCHEDULING AND PROGRESS MEASUREMENT PROCEDURE | 2020-09-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-006 | PRC | 6 | 082623C-0000-PP-0307 | 0 | B | IFA | CHANGE ORDER PROCEDURE | 2020-11-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-007 | PRC | 7 | 082623C-0000-PP-0118 | 0 | B | IFA | PERMITTING PLAN FOR EPCC PHASE | 2020-11-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-008 | PRC | 8 | 082623C-0000-PP-0107 | 0 | B | IFA | PROJECT DOCUMENT CODING | 2020-09-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-009 | PRC | 9 | 082623C-0000-PP-0501 | 0 | B | IFA | PROJECT QUALITY PLAN | 2020-11-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-010 | PRC | 10 | 082623C-0000-PP-0106 | 0 | B | IFA | PROJECT TAGGING PROCEDURE | 2020-09-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-011 | PRC | 11 | 082623C-0000-PP-0102 | 0 | B | IFA | PROJECT COORDINATION AND COMMUNICATION PROCEDURE | 2020-09-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-012 | PRC | 12 | 082623C-0000-PP-0401 | 0 | B | IFA | CHANGE INVOICING PROCEDURE | 2020-11-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-013 | PRC | 13 | 082623C-0000-PP-0119 | 0 | B | IFA | INTERFACE MANAGEMENT PLAN | 2020-09-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRC-014 | PRC | 14 | 082623C-0000-PP-0551 | 0 | B | IFA | PROJECT HSE PLAN | 2020-11-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-PRO-001 | PRO | 1 | 082623C-0000-SL-0001-0001 | 0 | B | IFA | APPROVED VENDOR LISTS (AVL) | 2020-11-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-RPT-001 | RPT | 1 | 082623C-0000-RR-0101 | 0 | B | IFI | MONTHLY FEED PROJECT STATUS REPORTS | 2020-09-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-RPT-002 | RPT | 2 | 082623C-0000-RR-0102 | 0 | B | IFI | MONTHLY FEED PROJECT STATUS REPORTS | 2020-10-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-RPT-003 | RPT | 3 | 082623C-0000-RR-0103 | 0 | B | IFI | MONTHLY FEED PROJECT STATUS REPORTS | 2020-11-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-RPT-004 | RPT | 4 | 082623C-0000-RR-0104 | 0 | B | IFI | MONTHLY FEED PROJECT STATUS REPORTS | 2020-12-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-RPT-005 | RPT | 5 | 082623C-0000-RR-0105 | 0 | B | IFI | MONTHLY FEED PROJECT STATUS REPORTS | 2021-01-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-RPT-006 | RPT | 6 | 082623C-0000-RR-0106 | 0 | B | IFI | MONTHLY FEED PROJECT STATUS REPORTS | 2021-02-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-RPT-007 | RPT | 7 | 082623C-0000-RR-0107 | 0 | B | IFI | MONTHLY FEED PROJECT STATUS REPORTS | 2021-03-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-STY-001 | STY | 1 | 082623C-0000-ML-0603 | 0 | B | IFI | SHIPPING AND LOGISTIC STUDY | 2021-02-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-DWG-001 | DWG | 1 | 082623C-0000-DW-1422-0001 | 0 | B | IFA | SOIL INVESTIGATION PLAN | 2021-01-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-DWG-002 | DWG | 2 | 082623C-0000-DW-1402-0001 | 0 | B | IFA | GENERAL NOTES FOR UNDERGROUND WORKS | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-DWG-003 | DWG | 3 | 082623C-0000-DW-1425-0001 | 0 | B | IFA | ROADS AND PAVING | 2021-01-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-DWG-004 | DWG | 4 | 082623C-0000-DW-1442-0001 | 0 | B | IFA | MAJOR UNDERGROUND | 2020-11-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-DWG-005 | DWG | 5 | 082623C-0000-DW-1421-0001 | 0 | B | IFA | SITE PREPARATION DRAWING | 2021-02-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-DWG-006 | DWG | 6 | 082623C-0000-DW-1702-0001 | 0 | B | IFA | GENERAL NOTES FOR CONCRETE WORKS | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-DWG-007 | DWG | 7 | 082623C-0000-DW-1802-0001 | 0 | B | IFA | GENERAL NOTES FOR STEEL STRUCTURE | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-LAY-001 | LAY | 1 | 082623C-0000-DW-1742-0001 | 0 | B | IFA | CONCEPTUAL LAYOUT PIPERACK | 2021-01-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-LAY-002 | LAY | 2 | 082623C-0000-DW-1742-0002 | 0 | B | IFA | CONCEPTUAL LAYOUT STRUCTURE | 2021-01-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-LAY-003 | LAY | 3 | 082623C-0000-DW-1742-0003 | 0 | B | IFA | CONCEPTUAL LAYOUT SHELTER | 2021-01-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-LAY-004 | LAY | 4 | 082623C-0000-DW-1742-0004 | 0 | B | IFA | INTERFACE POINT LAYOUT | 2020-11-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-SPC-001 | SPC | 1 | 082623C-0000-MS-1410-0001 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR SOIL INVESTIGATION | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-SPC-002 | SPC | 2 | 082623C-0000-JSD-1400-0001 | 0 | B | IFA | JOB DESIGN SPECIFICATION FOR UNDERGROUND SYSTEM WORKS | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-SPC-003 | SPC | 3 | 082623C-0000-JSD-1410-0001 | 0 | B | IFA | JSD FOR GEOTECHNICAL RECOMMENDATIONS | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-SPC-004 | SPC | 4 | 082623C-0000-JSD-1700-0001 | 0 | B | IFA | JSD FOR FOUNDATION AND STRUCTURES | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-STD-001 | STD | 1 | 082623C-0000-STD-1780-0001 | 0 | B | IFA | DESIGN STANDARDS FOR CONCRETE WORKS | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-STD-002 | STD | 2 | 082623C-0000-STD-1880-0001 | 0 | B | IFA | DESIGN STANDARDS FOR STEEL STRUCTURES | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 0000 | A8RX-TSC-0000-210-STD-003 | STD | 3 | 082623C-0000-STD-1480-0001 | 0 | B | IFA | DESIGN STANDARDS FOR UNDERGROUND WORKS | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-001 | LAY | 1 | 082623C-4100-DW-2021-0001 | 0 | B | IFA | MAIN CONTROL ROOM CONCEPTUAL LAYOUT - PLAN | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-002 | LAY | 2 | 082623C-4100-DW-2021-0002 | 0 | B | IFA | MAIN CONTROL ROOM CONCEPTUAL LAYOUT - SECTIONS AND ELEVATIONS | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-003 | LAY | 3 | 082623C-4100-DW-2022-0001 | 0 | B | IFA | OPR-82/TIR DS BUILDING CONCEPTUAL LAYOUT - PLAN | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-004 | LAY | 4 | 082623C-4100-DW-2022-0002 | 0 | B | IFA | OPR-82/TIR DS BUILDING CONCEPTUAL LAYOUT - SECTIONS AND ELEVATIONS | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-005 | LAY | 5 | 082623C-4100-DW-2022-0003 | 0 | B | IFA | OPT-711/TIR SC3 CONCEPTUAL LAYOUT - PLAN | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-006 | LAY | 6 | 082623C-4100-DW-2022-0004 | 0 | B | IFA | OPT-711/TIR SC3 CONCEPTUAL LAYOUT - SECTIONS AND ELEVATIONS | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-007 | LAY | 7 | 082623C-4100-DW-2022-0005 | 0 | B | IFA | OPR-71/TIR SC1 CONCEPTUAL LAYOUT - PLAN | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-008 | LAY | 8 | 082623C-4100-DW-2022-0006 | 0 | B | IFA | OPR-71/TIR SC1 CONCEPTUAL LAYOUT - SECTIONS AND ELEVATIONS | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-009 | LAY | 9 | 082623C-4100-DW-2022-0007 | 0 | B | IFA | OPT-712/TIR SC2 CONCEPTUAL LAYOUT - PLAN | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-010 | LAY | 10 | 082623C-4100-DW-2022-0008 | 0 | B | IFA | OPT-712/TIR SC2 CONCEPTUAL LAYOUT - SECTIONS AND ELEVATIONS | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-011 | LAY | 11 | 082623C-4100-DW-2022-0009 | 0 | B | IFA | OPR-75 CONCEPTUAL LAYOUT - PLAN | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LAY-012 | LAY | 12 | 082623C-4100-DW-2022-0010 | 0 | B | IFA | OPR-75 CONCEPTUAL LAYOUT - SECTIONS AND ELEVATIONS | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-LST-001 | LST | 1 | 082623C-0000-NM-2000-0001 | 0 | B | IFA | BUILDINGS LIST (INCLUDING SIZES, LEVELS, TYPE OF CONSTRUCTION AND BLAST RESISTANCE) | 2021-01-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 0000 | A8RX-TSC-0000-220-SPC-001 | SPC | 1 | 082623-0000-JSD-2000-0001 | 0 | B | IFA | JOB DESIGN SPECIFICATION FOR BUILDINGS | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PFD-001 | PFD | 1 | 082623C-0000-PFD-0010-0001 | 0 | B | IFA | OVERALL BLOCK FLOW DIAGRAM (SUMMER/WINTER) | 2020-10-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PHL-001 | PHL | 1 | 082623C-0000-JSD-0000-0003 | 0 | B | IFA | WINTERIZATION PHILOSOPHY | 2020-09-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PHL-002 | PHL | 2 | 082623C-0000-JSD-0000-0005 | 0 | B | IFA | EMERGENCY ISOLATION PHILOSOPHY | 2020-09-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PHL-003 | PHL | 3 | 082623C-0000-JSD-0000-0007 | 0 | B | IFA | DRAINAGE PHILOSOPHY | 2020-10-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PHL-004 | PHL | 4 | 082623C-0000-JSD-0000-0004 | 0 | B | IFA | BATTERY LIMIT AND MECHANICAL ISOLATION PHILOSOPHY | 2020-09-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PHL-005 | PHL | 5 | 082623-0000-JSD-0000-0001 | 0 | B | IFA | BASIC ENGINEERING DESIGN DATA (BEDD) | 2020-09-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PHL-006 | PHL | 6 | 082623-0000-JSD-0000-0002 | 0 | B | IFA | BASIC PROCESS DESIGN REQUIREMENTS AND CRITERIA | 2020-09-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-001 | PID | 1 | 082623C-0000-PID-0090-0001 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-002 | PID | 2 | 082623C-0000-PID-0090-0002 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-003 | PID | 3 | 082623C-0000-PID-0090-0003 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-004 | PID | 4 | 082623C-0000-PID-0090-0004 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-005 | PID | 5 | 082623C-0000-PID-0090-0005 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-006 | PID | 6 | 082623C-0000-PID-0090-0006 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-007 | PID | 7 | 082623C-0000-PID-0090-0007 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-008 | PID | 8 | 082623C-0000-PID-0090-0008 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-009 | PID | 9 | 082623C-0000-PID-0090-0009 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-010 | PID | 10 | 082623C-0000-PID-0090-0010 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-011 | PID | 11 | 082623C-0000-PID-0090-0011 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-012 | PID | 12 | 082623C-0000-PID-0090-0012 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-013 | PID | 13 | 082623C-0000-PID-0090-0013 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-014 | PID | 14 | 082623C-0000-PID-0090-0014 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-015 | PID | 15 | 082623C-0000-PID-0090-0015 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-016 | PID | 16 | 082623C-0000-PID-0090-0016 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-017 | PID | 17 | 082623C-0000-PID-0090-0017 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-018 | PID | 18 | 082623C-0000-PID-0090-0018 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-019 | PID | 19 | 082623C-0000-PID-0090-0019 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-020 | PID | 20 | 082623C-0000-PID-0090-0020 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-021 | PID | 21 | 082623C-0000-PID-0090-0021 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-022 | PID | 22 | 082623C-0000-PID-0090-0022 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-023 | PID | 23 | 082623C-0000-PID-0090-0023 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-024 | PID | 24 | 082623C-0000-PID-0090-0024 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-025 | PID | 25 | 082623C-0000-PID-0090-0025 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-026 | PID | 26 | 082623C-0000-PID-0090-0026 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-027 | PID | 27 | 082623C-0000-PID-0090-0027 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-028 | PID | 28 | 082623C-0000-PID-0090-0028 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-029 | PID | 29 | 082623C-0000-PID-0090-0029 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-030 | PID | 30 | 082623C-0000-PID-0090-0030 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-031 | PID | 31 | 082623C-0000-PID-0090-0031 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-032 | PID | 32 | 082623C-0000-PID-0090-0032 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-033 | PID | 33 | 082623C-0000-PID-0090-0033 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-034 | PID | 34 | 082623C-0000-PID-0090-0034 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-035 | PID | 35 | 082623C-0000-PID-0090-0035 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-036 | PID | 36 | 082623C-0000-PID-0090-0036 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 0000 | A8RX-TSC-0000-225-PID-037 | PID | 37 | 082623C-0000-PID-0090-0037 | 0 | B | IFA | LEGEND SHEETS PID | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 235 | HVAC | 0000 | A8RX-TSC-0000-235-SPC-001 | SPC | 1 | 082623-0000-JSD-3400-0001 | 0 | B | IFA | JOB DESIGN SPECIFICATION FOR HVAC SYSTEMS | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-LST-001 | LST | 1 | 082623C-0000-NM-1300-0001 | 0 | B | IFI | PIPING SPECIAL ITEMS LIST | 2020-12-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-PLN-001 | PLN | 1 | 082623C-0000-DW-0051-0001 | 0 | B | IFA | OVERALL PLOT-PLANS | 2020-10-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-PLN-002 | PLN | 2 | 082623C-0000-DW-0051-0002 | 0 | B | IFA | GENERAL PLOT PLANS | 2020-10-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-PLN-003 | PLN | 3 | 082623C-0000-DW-0052-0001 | 0 | B | IFA | WBS PLOT PLAN | 2020-10-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-PLN-004 | PLN | 4 | 082623C-0000-DW-0053-0001 | 0 | B | IFA | GENERAL KEY-PLANS | 2020-10-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-SPC-001 | SPC | 1 | 082623C-0000-JSD-1300-0008 | 0 | B | IFA | JSD FOR PIPING STRESS ANALYSIS | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-SPC-002 | SPC | 2 | 082623C-0000-JSD-1300-0001 | 0 | B | IFA | PIPING CLASSES SUMMARY | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-SPC-003 | SPC | 3 | 082623-0000-JSD-1300-0004 | 0 | B | IFA | JOB DESIGN SPECIFICATION FOR JACKETED PIPING | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-SPC-004 | SPC | 4 | 082623-0000-JSD-1300-0002 | 0 | B | IFA | JOB DESIGN SPECIFICATION FOR PIPING | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-SPC-005 | SPC | 5 | 082623-0000-JSD-1300-0003 | 0 | B | IFA | JOB DESIGN SPECIFICATION FOR STEAM TRACING | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-SPC-006 | SPC | 6 | 082623-0000-JSD-1300-0005 | 0 | B | IFA | JOB DESIGN SPECIFICATION HOT WATER / OIL TRACING | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-SPC-007 | SPC | 7 | 082623-0000-JSD-1300-0010 | 0 | B | IFA | JSD AUXILIARY STD PIPE SUPPORTS | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 0000 | A8RX-TSC-0000-250-SPC-008 | SPC | 8 | 082623-0000-JSD-1300-0009 | 0 | B | IFA | JSD STATIC LOAD ON PIPE SUPPORTS | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 0000 | A8RX-TSC-0000-255-LST-201 | LST | 201 | 0000-RA-E-20002 | 0 | C | IFI | SPARE PART LIST FOR STATIC EQUIPMENT | 2021-03-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-LST-501 | LST | 501 | 0000-MA-E-30010 | 0 | C | IFI | SPARE PART LIST FOR ROTATING EQUIPMENT | 2021-03-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-LST-502 | LST | 502 | 0000-MA-E-30011 | 0 | C | IFI | LUBRICANT LIST FOR ROTATING EQUIPMENT | 2021-03-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-HEATERS & BOILERS | 0000 | A8RX-TSC-0000-255-PRO-001 | PRO | 1 | 082623C-0000-TBT-0150-0001 | 0 | B | IFA | TBT WATER TUBE BOILERS | 2021-03-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 0000 | A8RX-TSC-0000-255-PRO-200 | PRO | 200 | 082623C-0000-TBT-0411-0001 | 0 | B | IFI | TBT FOR SHOP ASSEMBLED RACTORS -LLI | 2021-03-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 0000 | A8RX-TSC-0000-255-PRO-201 | PRO | 201 | 082623C-0000-TBT-0511-0001 | 0 | B | IFI | TECHNICAL BID TABULATION FOR SHOP ASSEMBLED COLUMNS - LLI | 2021-03-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 0000 | A8RX-TSC-0000-255-PRO-202 | PRO | 202 | 082623C-0000-TBT-0662-0001 | 0 | B | IFI | TBT FOR BRAZED ALUMINUM PLATE-FINS EXCHANGERS, INCLUDING THE MAIN COLD BOX | 2021-03-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-PRO-500 | PRO | 500 | 082623C-0000-TBT-0910-0001 | 0 | B | IFI | TBT CENTRIFUGAL PUMPS (BFW) | 2021-03-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-PRO-501 | PRO | 501 | 082623C-0000-TBT-1011-0001 | 0 | B | IFI | TBT CENTRIFUGAL COMPRESSORS - LLI | 2021-03-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-PRO-502 | PRO | 502 | 082623C-0000-TBT-1011-0002 | 0 | B | IFI | TBT CENTRIFUGAL COMPRESSORS - LLI - HD2 CENTRIFUGAL COMPRESSOR | 2021-03-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-PRO-503 | PRO | 503 | 082623C-0000-TBT-4121-0001 | 0 | B | IFI | TBT STEAM TURBINE GENERATOR | 2021-03-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-HEATERS & BOILERS | 0000 | A8RX-TSC-0000-255-SPC-001 | SPC | 1 | 082623C-0000-MR-0150-0001 | 0 | B | IFA | MR WATER TUBE BOILERS | 2020-12-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-HEATERS & BOILERS | 0000 | A8RX-TSC-0000-255-SPC-002 | SPC | 2 | 082623-0000-JSD-0110-0001 | 0 | B | IFA | JSD FOR FIRED HEATERS | 2020-11-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-HEATERS & BOILERS | 0000 | A8RX-TSC-0000-255-SPC-003 | SPC | 3 | 082623-0000-JSD-0150-0001 | 0 | B | IFA | JSD FOR STEAM BOILER | 2020-11-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 0000 | A8RX-TSC-0000-255-SPC-200 | SPC | 200 | 082623C-0000-MR-0411-0001 | 0 | B | IFA | MR FOR SHOP ASSEMBLED RACTORS -LLI | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 0000 | A8RX-TSC-0000-255-SPC-201 | SPC | 201 | 082623C-0000-MR-0511-0001 | 0 | B | IFA | MATERIAL REQUISITION FOR SHOP ASSEMBLED COLUMNS - LLI | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 0000 | A8RX-TSC-0000-255-SPC-202 | SPC | 202 | 082623C-0000-MR-0662-0001 | 0 | B | IFA | MR FOR BRAZED ALUMINUM PLATE-FINS EXCHANGERS, INCLUDING THE MAIN COLD BOX | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-SPC-500 | SPC | 500 | 082623C-0000-MR-0910-0001 | 0 | B | IFA | MR CENTRIFUGAL PUMPS (BFW) | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-SPC-501 | SPC | 501 | 082623C-0000-MR-1011-0001 | 0 | B | IFA | MR CENTRIFUGAL COMPRESSORS - LLI | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-SPC-502 | SPC | 502 | 082623C-0000-MR-1011-0002 | 0 | B | IFA | MR CENTRIFUGAL COMPRESSORS - LLI - HD2 CENTRIFUGAL COMPRESSOR | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 0000 | A8RX-TSC-0000-255-SPC-503 | SPC | 503 | 082623C-0000-MR-4121-0001 | 0 | B | IFA | MR STEAM TURBINE GENERATOR | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 0000 | A8RX-TSC-0000-265-LAY-001 | LAY | 1 | 0000-EB-A-40041 | 0 | B | IFA | ELECTRICAL OVERALL MAIN CABLE ROUTING | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 0000 | A8RX-TSC-0000-270-LAY-001 | LAY | 1 | 0000-HB-A-55001 | 0 | B | IFA | INSTRUMENT OVERALL MAIN CABLE ROUTING | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 0000 | A8RX-TSC-0000-270-SPC-001 | SPC | 1 | 0000-SA-E-50001 | 0 | B | IFA | INSTRUMENT TYPE SELECTION | 2021-02-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 0000 | A8RX-TSC-0000-500-CWP-001 | CWP | 1 | 0000-ZA-E-02004 | 0 | B | IFA | EPCC SITE LOGISTICS PLAN | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 0000 | A8RX-TSC-0000-500-ELS-001 | ELS | 1 | 082623C-0000-DW-6810-0001 | 0 | B | IFI | LIFTING STUDY | 2021-02-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 0000 | A8RX-TSC-0000-500-PRC-001 | PRC | 1 | 082623C-0000-PP-0825 | 0 | B | IFA | EPCC SITE LOGISTICS PLAN | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 0000 | A8RX-TSC-0000-500-PRC-002 | PRC | 2 | 082623C-0000-PP-0805 | 0 | B | IFA | PROJECT CONSTRUCTABILITY PROCEDURE | 2020-12-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 0000 | A8RX-TSC-0000-500-RPT-001 | RPT | 1 | 082623C-0000-RT-0801 | 0 | B | IFI | SUMMARY OF SITE VISIT REPORT | 2020-11-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-CAL-001 | CAL | 1 | 0000-ZX-E-80008 | 0 | B | IFA | FIREWATER DEMAND CALCULATION REPORT | 2020-12-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-DBD-001 | DBD | 1 | 0000-ZA-E-89001 | 0 | B | IFA | ENVIRONMENTAL DESIGN CRITERIA | 2020-11-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-HAC-001 | HAC | 1 | 0000-ZX-E-80009 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION REPORT | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-LAY-001 | LAY | 1 | 0000-ZB-A-85000 | 0 | B | IFA | FIREWATER OVERALL DISTRIBUTION LAYOUT | 2021-01-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-LAY-002 | LAY | 2 | 0000-ZB-A-85014 | 0 | B | IFI | SAFETY SHOWERS LAYOUT | 2021-02-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-PID-001 | PID | 1 | 0000-PD-B-85001 | 0 | B | IFA | PID - FIREWATER SYSTEM DISTRIBUTION - 1 | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-PID-002 | PID | 2 | 0000-PD-B-85002 | 0 | B | IFA | PID - FIREWATER SYSTEM DISTRIBUTION - 2 | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-PID-003 | PID | 3 | 0000-PD-B-85003 | 0 | B | IFA | PID - FIREWATER SYSTEM DISTRIBUTION - 3 | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-PID-004 | PID | 4 | 0000-PD-B-85004 | 0 | B | IFA | PID - FIREWATER SYSTEM DISTRIBUTION - 4 | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-QRA-001 | QRA | 1 | 0000-ZX-E-80010 | 0 | C | IFA | QUANTITATIVE RISK ANALYSIS AND BUILDING RISK ASSESSMENT REPORT | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-RPT-001 | RPT | 1 | 0000-ZX-E-80005 | 0 | B | IFI | HAZID REPORT | 2021-03-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-RPT-002 | RPT | 2 | 0000-ZX-E-80006 | 0 | C | IFI | HAZOP REPORT | 2021-03-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-RPT-003 | RPT | 3 | 0000-ZX-E-80007 | 0 | C | IFI | SIL DETERMINATION REPORT | 2021-03-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-RPT-004 | RPT | 4 | 0000-ZX-E-89003 | 0 | C | IFA | OVERALL NOISE STUDY | 2021-02-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-RPT-005 | RPT | 5 | 0000-ZX-E-89004 | 0 | C | IFA | TECHNICAL INPUT FOR ENVIRONMENTAL PERMIT | 2021-02-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-SPC-001 | SPC | 1 | 0000-ZA-E-80000 | 0 | B | IFA | HSE PROTECTION PHYLOSOPHY | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-SPC-002 | SPC | 2 | 0000-ZA-E-80001 | 0 | B | IFA | FIRE AND GAS DETECTION SYSTEM SPECIFICATION | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-SPC-003 | SPC | 3 | 0000-ZA-E-80002 | 0 | B | IFA | FIRE PROTECTION SYSTEM SPECIFICATION | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-TOR-001 | TOR | 1 | 0000-ZA-E-80003 | 0 | B | IFA | HAZID TERMS OF REFERENCE | 2020-09-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 0000 | A8RX-TSC-0000-653-TOR-002 | TOR | 2 | 0000-ZA-E-80004 | 0 | B | IFA | HAZOP/SIL TERMS OF REFERENCE | 2021-01-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-SCH-001 | SCH | 1 | 082623C-0000-PLG-0305 | 0 | B | IFA | MASTER PROJECT SCHEDULE FEED L3 | 2020-08-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 0000 | A8RX-TSC-0000-200-SCH-002 | SCH | 2 | 082623C-0000-PLG-0315 | 0 | B | IFA | EPCC SCHEDULE | 2021-03-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 2000 | A8RX-TSC-2000-210-DWG-001 | DWG | 1 | 082623C-2000-DW-1442-0001 | 0 | B | IFA | MAJOR UNDERGROUND CRACKER | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-DBD-001 | DBD | 1 | 082623C-2000-CN-0007-0001 | 0 | B | IFA | PROCESS DESIGN BASIS - STEAM CRACKER | 2020-08-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-DBD-002 | DBD | 2 | 082623C-2000-NM-0001-0001 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - STEAM CRACKER (SUMMER CASE) | 2020-09-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-DBD-003 | DBD | 3 | 082623C-2000-NM-0001-0002 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - STEAM CRACKER (WINTER CASE) | 2020-09-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-DBD-004 | DBD | 4 | 082623C-2000-NM-0001-0004 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - STEAM CRACKER (RATING CASE) | 2020-09-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-DST-001 | DST | 1 | 082623C-2000-SP-1500-0045 | 0 | B | IFI | DS FOR SAFETY MATL (PSV, TRV, BREATHER VALVES) - STEAM CRACKER | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-DST-002 | DST | 2 | 082623C-2000-SP-1500-0041 | 0 | B | IFI | DS FOR CRITICAL CONTROL VALVES - STEAM CRACKER | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-DST-003 | DST | 3 | 082623C-2000-SP-1500-0001 | 0 | B | IFI | DS FOR ANALYZERS - STEAM CRACKER | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-001 | MSD | 1 | 082623C-2000-MSD-0011-0001 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-002 | MSD | 2 | 082623C-2000-MSD-0011-0002 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-003 | MSD | 3 | 082623C-2000-MSD-0011-0003 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-004 | MSD | 4 | 082623C-2000-MSD-0011-0004 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-005 | MSD | 5 | 082623C-2000-MSD-0011-0005 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-006 | MSD | 6 | 082623C-2000-MSD-0011-0006 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-007 | MSD | 7 | 082623C-2000-MSD-0011-0007 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-008 | MSD | 8 | 082623C-2000-MSD-0011-0008 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-009 | MSD | 9 | 082623C-2000-MSD-0011-0009 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-010 | MSD | 10 | 082623C-2000-MSD-0011-0010 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-011 | MSD | 11 | 082623C-2000-MSD-0011-0011 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-012 | MSD | 12 | 082623C-2000-MSD-0011-0012 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-013 | MSD | 13 | 082623C-2000-MSD-0011-0013 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-014 | MSD | 14 | 082623C-2000-MSD-0011-0014 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-015 | MSD | 15 | 082623C-2000-MSD-0011-0015 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-016 | MSD | 16 | 082623C-2000-MSD-0011-0016 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-017 | MSD | 17 | 082623C-2000-MSD-0011-0017 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-018 | MSD | 18 | 082623C-2000-MSD-0011-0018 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-019 | MSD | 19 | 082623C-2000-MSD-0011-0019 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-020 | MSD | 20 | 082623C-2000-MSD-0011-0020 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-021 | MSD | 21 | 082623C-2000-MSD-0011-0021 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-022 | MSD | 22 | 082623C-2000-MSD-0011-0022 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-023 | MSD | 23 | 082623C-2000-MSD-0011-0023 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-024 | MSD | 24 | 082623C-2000-MSD-0011-0024 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-025 | MSD | 25 | 082623C-2000-MSD-0011-0025 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-026 | MSD | 26 | 082623C-2000-MSD-0011-0026 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-027 | MSD | 27 | 082623C-2000-MSD-0011-0027 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-028 | MSD | 28 | 082623C-2000-MSD-0011-0028 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-029 | MSD | 29 | 082623C-2000-MSD-0011-0029 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-030 | MSD | 30 | 082623C-2000-MSD-0011-0030 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-031 | MSD | 31 | 082623C-2000-MSD-0011-0031 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-032 | MSD | 32 | 082623C-2000-MSD-0011-0032 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-033 | MSD | 33 | 082623C-2000-MSD-0011-0033 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-034 | MSD | 34 | 082623C-2000-MSD-0011-0034 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-035 | MSD | 35 | 082623C-2000-MSD-0011-0035 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-036 | MSD | 36 | 082623C-2000-MSD-0011-0036 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-037 | MSD | 37 | 082623C-2000-MSD-0011-0037 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-MSD-038 | MSD | 38 | 082623C-2000-MSD-0011-0038 | 0 | B | IFA | MATERIAL SELECTION DIAGRAMS - STEAM CRACKER | 2020-11-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-NAR-001 | NAR | 1 | 082623C-2000-CN-0009-0001 | 0 | B | IFA | PROCESS DESCRIPTION - STEAM CRACKER UNITS | 2020-08-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-NAR-002 | NAR | 2 | 082623C-2000-CN-0008-0001 | 0 | B | IFI | CONTROL NARRATIVES - COMPLEX LOOPS - STEAM CRACKING | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-001 | PFD | 1 | 082623C-2000-PFD-0010-0001 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-039 | PFD | 39 | 082623C-2000-PFD-0010-0039 | 0 | B | IFA | BLOCK FLOW DIAGRAM - STEAM CRACKER UNITS | 2020-09-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-040 | PFD | 40 | 082623C-3300-PFD-0010-0040 | 0 | B | IFA | BLOCK FLOW DIAGRAM - STYRENE EXTRACTION UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-041 | PFD | 41 | 082623C-3400-PFD-0010-0041 | 0 | B | IFA | BLOCK FLOW DIAGRAM - PYGAS HYDROGENATION UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-111 | PFD | 111 | 082623C-2000-PFD-0010-0111 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-211 | PFD | 211 | 082623C-2000-PFD-0010-0211 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-212 | PFD | 212 | 082623C-2000-PFD-0010-0212 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-213 | PFD | 213 | 082623C-2000-PFD-0010-0213 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-214 | PFD | 214 | 082623C-2000-PFD-0010-0214 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-311 | PFD | 311 | 082623C-2000-PFD-0010-0311 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-312 | PFD | 312 | 082623C-2000-PFD-0010-0312 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-313 | PFD | 313 | 082623C-2000-PFD-0010-0313 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-314 | PFD | 314 | 082623C-2000-PFD-0010-0314 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-315 | PFD | 315 | 082623C-2000-PFD-0010-0315 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-316 | PFD | 316 | 082623C-2000-PFD-0010-0316 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-317 | PFD | 317 | 082623C-2000-PFD-0010-0317 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-318 | PFD | 318 | 082623C-2000-PFD-0010-0318 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-411 | PFD | 411 | 082623C-2000-PFD-0010-0411 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-412 | PFD | 412 | 082623C-2000-PFD-0010-0412 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-413 | PFD | 413 | 082623C-2000-PFD-0010-0413 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-414 | PFD | 414 | 082623C-2000-PFD-0010-0414 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-415 | PFD | 415 | 082623C-2000-PFD-0010-0415 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-416 | PFD | 416 | 082623C-2000-PFD-0010-0416 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-511 | PFD | 511 | 082623C-2000-PFD-0010-0511 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-512 | PFD | 512 | 082623C-2000-PFD-0010-0512 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-513 | PFD | 513 | 082623C-2000-PFD-0010-0513 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-611 | PFD | 611 | 082623C-2000-PFD-0010-0611 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-612 | PFD | 612 | 082623C-2000-PFD-0010-0612 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-613 | PFD | 613 | 082623C-2000-PFD-0010-0613 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-614 | PFD | 614 | 082623C-2000-PFD-0010-0614 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-711 | PFD | 711 | 082623C-2000-PFD-0010-0711 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-911 | PFD | 911 | 082623C-2000-PFD-0010-0911 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-912 | PFD | 912 | 082623C-2000-PFD-0010-0912 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-913 | PFD | 913 | 082623C-2000-PFD-0010-0913 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-916 | PFD | 916 | 082623C-2000-PFD-0010-0916 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-918 | PFD | 918 | 082623C-2000-PFD-0010-0918 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PFD-919 | PFD | 919 | 082623C-2000-PFD-0010-0919 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STEAM CRACKER | 2020-09-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-001 | PID | 1 | 082623C-2000-PID-0021-0001 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-002 | PID | 2 | 082623C-2000-PID-0021-0002 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-003 | PID | 3 | 082623C-2000-PID-0021-0003 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-004 | PID | 4 | 082623C-2000-PID-0021-0004 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-005 | PID | 5 | 082623C-2000-PID-0021-0005 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-006 | PID | 6 | 082623C-2000-PID-0021-0006 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-007 | PID | 7 | 082623C-2000-PID-0021-0007 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-008 | PID | 8 | 082623C-2000-PID-0021-0008 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-009 | PID | 9 | 082623C-2000-PID-0021-0009 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-010 | PID | 10 | 082623C-2000-PID-0021-0010 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-011 | PID | 11 | 082623C-2000-PID-0021-0011 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-012 | PID | 12 | 082623C-2000-PID-0021-0012 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-013 | PID | 13 | 082623C-2000-PID-0021-0013 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-014 | PID | 14 | 082623C-2000-PID-0021-0014 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-015 | PID | 15 | 082623C-2000-PID-0021-0015 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-016 | PID | 16 | 082623C-2000-PID-0021-0016 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-017 | PID | 17 | 082623C-2000-PID-0021-0017 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-018 | PID | 18 | 082623C-2000-PID-0021-0018 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-019 | PID | 19 | 082623C-2000-PID-0021-0019 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-020 | PID | 20 | 082623C-2000-PID-0021-0020 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-021 | PID | 21 | 082623C-2000-PID-0021-0021 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-022 | PID | 22 | 082623C-2000-PID-0021-0022 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-023 | PID | 23 | 082623C-2000-PID-0021-0023 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-024 | PID | 24 | 082623C-2000-PID-0021-0024 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-025 | PID | 25 | 082623C-2000-PID-0021-0025 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-026 | PID | 26 | 082623C-2000-PID-0021-0026 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-027 | PID | 27 | 082623C-2000-PID-0021-0027 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-028 | PID | 28 | 082623C-2000-PID-0021-0028 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-029 | PID | 29 | 082623C-2000-PID-0021-0029 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-030 | PID | 30 | 082623C-2000-PID-0021-0030 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-031 | PID | 31 | 082623C-2000-PID-0021-0031 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-032 | PID | 32 | 082623C-2000-PID-0021-0032 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-033 | PID | 33 | 082623C-2000-PID-0021-0033 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-034 | PID | 34 | 082623C-2000-PID-0021-0034 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-035 | PID | 35 | 082623C-2000-PID-0021-0035 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-036 | PID | 36 | 082623C-2000-PID-0021-0036 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-037 | PID | 37 | 082623C-2000-PID-0021-0037 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-038 | PID | 38 | 082623C-2000-PID-0021-0038 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-039 | PID | 39 | 082623C-2000-PID-0021-0039 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-040 | PID | 40 | 082623C-2000-PID-0021-0040 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-041 | PID | 41 | 082623C-2000-PID-0021-0041 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-042 | PID | 42 | 082623C-2000-PID-0021-0042 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-043 | PID | 43 | 082623C-2000-PID-0021-0043 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-044 | PID | 44 | 082623C-2000-PID-0021-0044 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-045 | PID | 45 | 082623C-2000-PID-0021-0045 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-046 | PID | 46 | 082623C-2000-PID-0021-0046 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-047 | PID | 47 | 082623C-2000-PID-0021-0047 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-048 | PID | 48 | 082623C-2000-PID-0021-0048 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-049 | PID | 49 | 082623C-2000-PID-0021-0049 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-050 | PID | 50 | 082623C-2000-PID-0021-0050 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-051 | PID | 51 | 082623C-2000-PID-0021-0051 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-052 | PID | 52 | 082623C-2000-PID-0021-0052 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-053 | PID | 53 | 082623C-2000-PID-0021-0053 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-054 | PID | 54 | 082623C-2000-PID-0021-0054 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-055 | PID | 55 | 082623C-2000-PID-0021-0055 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-056 | PID | 56 | 082623C-2000-PID-0021-0056 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-057 | PID | 57 | 082623C-2000-PID-0021-0057 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-058 | PID | 58 | 082623C-2000-PID-0021-0058 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-059 | PID | 59 | 082623C-2000-PID-0021-0059 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-060 | PID | 60 | 082623C-2000-PID-0021-0060 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-061 | PID | 61 | 082623C-2000-PID-0021-0061 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-062 | PID | 62 | 082623C-2000-PID-0021-0062 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-063 | PID | 63 | 082623C-2000-PID-0021-0063 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-064 | PID | 64 | 082623C-2000-PID-0021-0064 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-065 | PID | 65 | 082623C-2000-PID-0021-0065 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-066 | PID | 66 | 082623C-2000-PID-0021-0066 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-067 | PID | 67 | 082623C-2000-PID-0021-0067 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-068 | PID | 68 | 082623C-2000-PID-0021-0068 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-069 | PID | 69 | 082623C-2000-PID-0021-0069 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-070 | PID | 70 | 082623C-2000-PID-0021-0070 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-071 | PID | 71 | 082623C-2000-PID-0021-0071 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-072 | PID | 72 | 082623C-2000-PID-0021-0072 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-073 | PID | 73 | 082623C-2000-PID-0021-0073 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-074 | PID | 74 | 082623C-2000-PID-0021-0074 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-075 | PID | 75 | 082623C-2000-PID-0021-0075 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-076 | PID | 76 | 082623C-2000-PID-0021-0076 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-077 | PID | 77 | 082623C-2000-PID-0021-0077 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-078 | PID | 78 | 082623C-2000-PID-0021-0078 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-079 | PID | 79 | 082623C-2000-PID-0021-0079 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-080 | PID | 80 | 082623C-2000-PID-0021-0080 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-081 | PID | 81 | 082623C-2000-PID-0021-0081 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-082 | PID | 82 | 082623C-2000-PID-0021-0082 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-083 | PID | 83 | 082623C-2000-PID-0021-0083 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-084 | PID | 84 | 082623C-2000-PID-0021-0084 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-085 | PID | 85 | 082623C-2000-PID-0021-0085 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-086 | PID | 86 | 082623C-2000-PID-0021-0086 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-087 | PID | 87 | 082623C-2000-PID-0021-0087 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-088 | PID | 88 | 082623C-2000-PID-0021-0088 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-089 | PID | 89 | 082623C-2000-PID-0021-0089 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-090 | PID | 90 | 082623C-2000-PID-0021-0090 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-091 | PID | 91 | 082623C-2000-PID-0021-0091 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-092 | PID | 92 | 082623C-2000-PID-0021-0092 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-093 | PID | 93 | 082623C-2000-PID-0021-0093 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-094 | PID | 94 | 082623C-2000-PID-0021-0094 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-095 | PID | 95 | 082623C-2000-PID-0021-0095 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-096 | PID | 96 | 082623C-2000-PID-0021-0096 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-097 | PID | 97 | 082623C-2000-PID-0021-0097 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-098 | PID | 98 | 082623C-2000-PID-0021-0098 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-099 | PID | 99 | 082623C-2000-PID-0021-0099 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-100 | PID | 100 | 082623C-2000-PID-0021-0100 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-101 | PID | 101 | 082623C-2000-PID-0021-0101 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-102 | PID | 102 | 082623C-2000-PID-0021-0102 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-103 | PID | 103 | 082623C-2000-PID-0021-0103 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-104 | PID | 104 | 082623C-2000-PID-0021-0104 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-105 | PID | 105 | 082623C-2000-PID-0021-0105 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-106 | PID | 106 | 082623C-2000-PID-0021-0106 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-107 | PID | 107 | 082623C-2000-PID-0021-0107 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-108 | PID | 108 | 082623C-2000-PID-0021-0108 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-109 | PID | 109 | 082623C-2000-PID-0021-0109 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-110 | PID | 110 | 082623C-2000-PID-0021-0110 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-111 | PID | 111 | 082623C-2000-PID-0021-0111 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-112 | PID | 112 | 082623C-2000-PID-0021-0112 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-113 | PID | 113 | 082623C-2000-PID-0021-0113 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-114 | PID | 114 | 082623C-2000-PID-0021-0114 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-115 | PID | 115 | 082623C-2000-PID-0021-0115 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-116 | PID | 116 | 082623C-2000-PID-0021-0116 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-117 | PID | 117 | 082623C-2000-PID-0021-0117 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-118 | PID | 118 | 082623C-2000-PID-0021-0118 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-119 | PID | 119 | 082623C-2000-PID-0021-0119 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-120 | PID | 120 | 082623C-2000-PID-0021-0120 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-121 | PID | 121 | 082623C-2000-PID-0021-0121 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-122 | PID | 122 | 082623C-2000-PID-0021-0122 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-123 | PID | 123 | 082623C-2000-PID-0021-0123 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-124 | PID | 124 | 082623C-2000-PID-0021-0124 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-125 | PID | 125 | 082623C-2000-PID-0021-0125 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-126 | PID | 126 | 082623C-2000-PID-0021-0126 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-127 | PID | 127 | 082623C-2000-PID-0021-0127 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-128 | PID | 128 | 082623C-2000-PID-0021-0128 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-129 | PID | 129 | 082623C-2000-PID-0021-0129 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-130 | PID | 130 | 082623C-2000-PID-0021-0130 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-131 | PID | 131 | 082623C-2000-PID-0021-0131 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-132 | PID | 132 | 082623C-2000-PID-0021-0132 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-133 | PID | 133 | 082623C-2000-PID-0021-0133 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-134 | PID | 134 | 082623C-2000-PID-0021-0134 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-135 | PID | 135 | 082623C-2000-PID-0021-0135 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-136 | PID | 136 | 082623C-2000-PID-0021-0136 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-137 | PID | 137 | 082623C-2000-PID-0021-0137 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-138 | PID | 138 | 082623C-2000-PID-0021-0138 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-139 | PID | 139 | 082623C-2000-PID-0021-0139 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-140 | PID | 140 | 082623C-2000-PID-0021-0140 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-141 | PID | 141 | 082623C-2000-PID-0021-0141 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-142 | PID | 142 | 082623C-2000-PID-0021-0142 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-143 | PID | 143 | 082623C-2000-PID-0021-0143 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-144 | PID | 144 | 082623C-2000-PID-0021-0144 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-145 | PID | 145 | 082623C-2000-PID-0021-0145 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-146 | PID | 146 | 082623C-2000-PID-0021-0146 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-147 | PID | 147 | 082623C-2000-PID-0021-0147 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-148 | PID | 148 | 082623C-2000-PID-0021-0148 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-149 | PID | 149 | 082623C-2000-PID-0021-0149 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-150 | PID | 150 | 082623C-2000-PID-0021-0150 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-151 | PID | 151 | 082623C-2000-PID-0021-0151 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-152 | PID | 152 | 082623C-2000-PID-0021-0152 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-153 | PID | 153 | 082623C-2000-PID-0021-0153 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-154 | PID | 154 | 082623C-2000-PID-0021-0154 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-155 | PID | 155 | 082623C-2000-PID-0021-0155 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-156 | PID | 156 | 082623C-2000-PID-0021-0156 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-157 | PID | 157 | 082623C-2000-PID-0021-0157 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-158 | PID | 158 | 082623C-2000-PID-0021-0158 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-159 | PID | 159 | 082623C-2000-PID-0021-0159 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-160 | PID | 160 | 082623C-2000-PID-0021-0160 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-161 | PID | 161 | 082623C-2000-PID-0021-0161 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-162 | PID | 162 | 082623C-2000-PID-0021-0162 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-163 | PID | 163 | 082623C-2000-PID-0021-0163 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-164 | PID | 164 | 082623C-2000-PID-0021-0164 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-165 | PID | 165 | 082623C-2000-PID-0021-0165 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-166 | PID | 166 | 082623C-2000-PID-0021-0166 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-167 | PID | 167 | 082623C-2000-PID-0021-0167 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-168 | PID | 168 | 082623C-2000-PID-0021-0168 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-169 | PID | 169 | 082623C-2000-PID-0021-0169 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-170 | PID | 170 | 082623C-2000-PID-0021-0170 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-171 | PID | 171 | 082623C-2000-PID-0021-0171 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-172 | PID | 172 | 082623C-2000-PID-0021-0172 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-173 | PID | 173 | 082623C-2000-PID-0021-0173 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-174 | PID | 174 | 082623C-2000-PID-0021-0174 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-175 | PID | 175 | 082623C-2000-PID-0021-0175 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-176 | PID | 176 | 082623C-2000-PID-0021-0176 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-177 | PID | 177 | 082623C-2000-PID-0021-0177 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-178 | PID | 178 | 082623C-2000-PID-0021-0178 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-179 | PID | 179 | 082623C-2000-PID-0021-0179 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-180 | PID | 180 | 082623C-2000-PID-0021-0180 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-181 | PID | 181 | 082623C-2000-PID-0021-0181 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-182 | PID | 182 | 082623C-2000-PID-0021-0182 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-183 | PID | 183 | 082623C-2000-PID-0021-0183 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-184 | PID | 184 | 082623C-2000-PID-0021-0184 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-185 | PID | 185 | 082623C-2000-PID-0021-0185 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-186 | PID | 186 | 082623C-2000-PID-0021-0186 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-187 | PID | 187 | 082623C-2000-PID-0021-0187 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-188 | PID | 188 | 082623C-2000-PID-0021-0188 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-189 | PID | 189 | 082623C-2000-PID-0021-0189 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-190 | PID | 190 | 082623C-2000-PID-0021-0190 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-191 | PID | 191 | 082623C-2000-PID-0021-0191 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-192 | PID | 192 | 082623C-2000-PID-0021-0192 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-193 | PID | 193 | 082623C-2000-PID-0021-0193 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-194 | PID | 194 | 082623C-2000-PID-0021-0194 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-195 | PID | 195 | 082623C-2000-PID-0021-0195 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-196 | PID | 196 | 082623C-2000-PID-0021-0196 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-197 | PID | 197 | 082623C-2000-PID-0021-0197 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-198 | PID | 198 | 082623C-2000-PID-0021-0198 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-199 | PID | 199 | 082623C-2000-PID-0021-0199 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-200 | PID | 200 | 082623C-2000-PID-0021-0200 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-201 | PID | 201 | 082623C-2000-PID-0021-0201 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-202 | PID | 202 | 082623C-2000-PID-0021-0202 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-203 | PID | 203 | 082623C-2000-PID-0021-0203 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-204 | PID | 204 | 082623C-2000-PID-0021-0204 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-205 | PID | 205 | 082623C-2000-PID-0021-0205 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-206 | PID | 206 | 082623C-2000-PID-0021-0206 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-207 | PID | 207 | 082623C-2000-PID-0021-0207 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-208 | PID | 208 | 082623C-2000-PID-0021-0208 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-209 | PID | 209 | 082623C-2000-PID-0021-0209 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-210 | PID | 210 | 082623C-2000-PID-0021-0210 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-211 | PID | 211 | 082623C-2000-PID-0021-0211 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-212 | PID | 212 | 082623C-2000-PID-0021-0212 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-213 | PID | 213 | 082623C-2000-PID-0021-0213 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-214 | PID | 214 | 082623C-2000-PID-0021-0214 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-215 | PID | 215 | 082623C-2000-PID-0021-0215 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-216 | PID | 216 | 082623C-2000-PID-0021-0216 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-217 | PID | 217 | 082623C-2000-PID-0021-0217 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-218 | PID | 218 | 082623C-2000-PID-0021-0218 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-219 | PID | 219 | 082623C-2000-PID-0021-0219 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-220 | PID | 220 | 082623C-2000-PID-0021-0220 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-221 | PID | 221 | 082623C-2000-PID-0021-0221 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-222 | PID | 222 | 082623C-2000-PID-0021-0222 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-223 | PID | 223 | 082623C-2000-PID-0021-0223 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-224 | PID | 224 | 082623C-2000-PID-0021-0224 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-225 | PID | 225 | 082623C-2000-PID-0021-0225 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-226 | PID | 226 | 082623C-2000-PID-0021-0226 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-227 | PID | 227 | 082623C-2000-PID-0021-0227 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-228 | PID | 228 | 082623C-2000-PID-0021-0228 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-229 | PID | 229 | 082623C-2000-PID-0021-0229 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-230 | PID | 230 | 082623C-2000-PID-0021-0230 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-231 | PID | 231 | 082623C-2000-PID-0021-0231 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-232 | PID | 232 | 082623C-2000-PID-0021-0232 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-233 | PID | 233 | 082623C-2000-PID-0021-0233 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-234 | PID | 234 | 082623C-2000-PID-0021-0234 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-235 | PID | 235 | 082623C-2000-PID-0021-0235 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-236 | PID | 236 | 082623C-2000-PID-0021-0236 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-237 | PID | 237 | 082623C-2000-PID-0021-0237 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-238 | PID | 238 | 082623C-2000-PID-0021-0238 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-239 | PID | 239 | 082623C-2000-PID-0021-0239 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-240 | PID | 240 | 082623C-2000-PID-0021-0240 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-241 | PID | 241 | 082623C-2000-PID-0021-0241 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-242 | PID | 242 | 082623C-2000-PID-0021-0242 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-243 | PID | 243 | 082623C-2000-PID-0021-0243 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-244 | PID | 244 | 082623C-2000-PID-0021-0244 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-245 | PID | 245 | 082623C-2000-PID-0021-0245 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-246 | PID | 246 | 082623C-2000-PID-0021-0246 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-247 | PID | 247 | 082623C-2000-PID-0021-0247 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-248 | PID | 248 | 082623C-2000-PID-0021-0248 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-249 | PID | 249 | 082623C-2000-PID-0021-0249 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-250 | PID | 250 | 082623C-2000-PID-0021-0250 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-251 | PID | 251 | 082623C-2000-PID-0021-0251 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-252 | PID | 252 | 082623C-2000-PID-0021-0252 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-253 | PID | 253 | 082623C-2000-PID-0021-0253 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-254 | PID | 254 | 082623C-2000-PID-0021-0254 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-255 | PID | 255 | 082623C-2000-PID-0021-0255 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-256 | PID | 256 | 082623C-2000-PID-0021-0256 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-257 | PID | 257 | 082623C-2000-PID-0021-0257 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-258 | PID | 258 | 082623C-2000-PID-0021-0258 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-259 | PID | 259 | 082623C-2000-PID-0021-0259 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-260 | PID | 260 | 082623C-2000-PID-0021-0260 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-261 | PID | 261 | 082623C-2000-PID-0021-0261 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-262 | PID | 262 | 082623C-2000-PID-0021-0262 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-263 | PID | 263 | 082623C-2000-PID-0021-0263 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-264 | PID | 264 | 082623C-2000-PID-0021-0264 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-265 | PID | 265 | 082623C-2000-PID-0021-0265 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-266 | PID | 266 | 082623C-2000-PID-0021-0266 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-267 | PID | 267 | 082623C-2000-PID-0021-0267 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-268 | PID | 268 | 082623C-2000-PID-0021-0268 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-269 | PID | 269 | 082623C-2000-PID-0021-0269 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-270 | PID | 270 | 082623C-2000-PID-0021-0270 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-271 | PID | 271 | 082623C-2000-PID-0021-0271 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-272 | PID | 272 | 082623C-2000-PID-0021-0272 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-273 | PID | 273 | 082623C-2000-PID-0021-0273 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-274 | PID | 274 | 082623C-2000-PID-0021-0274 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-275 | PID | 275 | 082623C-2000-PID-0021-0275 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-276 | PID | 276 | 082623C-2000-PID-0021-0276 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-277 | PID | 277 | 082623C-2000-PID-0021-0277 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-278 | PID | 278 | 082623C-2000-PID-0021-0278 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-279 | PID | 279 | 082623C-2000-PID-0021-0279 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-280 | PID | 280 | 082623C-2000-PID-0021-0280 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-281 | PID | 281 | 082623C-2000-PID-0021-0281 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-282 | PID | 282 | 082623C-2000-PID-0021-0282 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-283 | PID | 283 | 082623C-2000-PID-0021-0283 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-284 | PID | 284 | 082623C-2000-PID-0021-0284 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-285 | PID | 285 | 082623C-2000-PID-0021-0285 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-286 | PID | 286 | 082623C-2000-PID-0021-0286 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-287 | PID | 287 | 082623C-2000-PID-0021-0287 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-288 | PID | 288 | 082623C-2000-PID-0021-0288 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-289 | PID | 289 | 082623C-2000-PID-0021-0289 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-290 | PID | 290 | 082623C-2000-PID-0021-0290 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-291 | PID | 291 | 082623C-2000-PID-0021-0291 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-292 | PID | 292 | 082623C-2000-PID-0021-0292 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-293 | PID | 293 | 082623C-2000-PID-0021-0293 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-294 | PID | 294 | 082623C-2000-PID-0021-0294 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-295 | PID | 295 | 082623C-2000-PID-0021-0295 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-296 | PID | 296 | 082623C-2000-PID-0021-0296 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-297 | PID | 297 | 082623C-2000-PID-0021-0297 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-298 | PID | 298 | 082623C-2000-PID-0021-0298 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-299 | PID | 299 | 082623C-2000-PID-0021-0299 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-300 | PID | 300 | 082623C-2000-PID-0021-0300 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-301 | PID | 301 | 082623C-2000-PID-0021-0301 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-302 | PID | 302 | 082623C-2000-PID-0021-0302 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-303 | PID | 303 | 082623C-2000-PID-0021-0303 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-304 | PID | 304 | 082623C-2000-PID-0021-0304 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-305 | PID | 305 | 082623C-2000-PID-0021-0305 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-306 | PID | 306 | 082623C-2000-PID-0021-0306 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-307 | PID | 307 | 082623C-2000-PID-0021-0307 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-308 | PID | 308 | 082623C-2000-PID-0021-0308 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-309 | PID | 309 | 082623C-2000-PID-0021-0309 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-310 | PID | 310 | 082623C-2000-PID-0021-0310 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-311 | PID | 311 | 082623C-2000-PID-0021-0311 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-312 | PID | 312 | 082623C-2000-PID-0021-0312 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-313 | PID | 313 | 082623C-2000-PID-0021-0313 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-314 | PID | 314 | 082623C-2000-PID-0021-0314 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-315 | PID | 315 | 082623C-2000-PID-0021-0315 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-316 | PID | 316 | 082623C-2000-PID-0021-0316 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-317 | PID | 317 | 082623C-2000-PID-0021-0317 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-318 | PID | 318 | 082623C-2000-PID-0021-0318 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-319 | PID | 319 | 082623C-2000-PID-0021-0319 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-320 | PID | 320 | 082623C-2000-PID-0021-0320 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-321 | PID | 321 | 082623C-2000-PID-0021-0321 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-322 | PID | 322 | 082623C-2000-PID-0021-0322 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-323 | PID | 323 | 082623C-2000-PID-0021-0323 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-324 | PID | 324 | 082623C-2000-PID-0021-0324 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-325 | PID | 325 | 082623C-2000-PID-0021-0325 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-326 | PID | 326 | 082623C-2000-PID-0021-0326 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-327 | PID | 327 | 082623C-2000-PID-0021-0327 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-328 | PID | 328 | 082623C-2000-PID-0021-0328 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-329 | PID | 329 | 082623C-2000-PID-0021-0329 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-330 | PID | 330 | 082623C-2000-PID-0021-0330 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-331 | PID | 331 | 082623C-2000-PID-0021-0331 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-332 | PID | 332 | 082623C-2000-PID-0021-0332 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-333 | PID | 333 | 082623C-2000-PID-0021-0333 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-334 | PID | 334 | 082623C-2000-PID-0021-0334 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-335 | PID | 335 | 082623C-2000-PID-0021-0335 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-336 | PID | 336 | 082623C-2000-PID-0021-0336 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-337 | PID | 337 | 082623C-2000-PID-0021-0337 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-338 | PID | 338 | 082623C-2000-PID-0021-0338 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-339 | PID | 339 | 082623C-2000-PID-0021-0339 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-340 | PID | 340 | 082623C-2000-PID-0021-0340 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-341 | PID | 341 | 082623C-2000-PID-0021-0341 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-342 | PID | 342 | 082623C-2000-PID-0021-0342 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-343 | PID | 343 | 082623C-2000-PID-0021-0343 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-344 | PID | 344 | 082623C-2000-PID-0021-0344 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-345 | PID | 345 | 082623C-2000-PID-0021-0345 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-346 | PID | 346 | 082623C-2000-PID-0021-0346 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-347 | PID | 347 | 082623C-2000-PID-0021-0347 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-348 | PID | 348 | 082623C-2000-PID-0021-0348 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-349 | PID | 349 | 082623C-2000-PID-0021-0349 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-350 | PID | 350 | 082623C-2000-PID-0021-0350 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-351 | PID | 351 | 082623C-2000-PID-0021-0351 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-352 | PID | 352 | 082623C-2000-PID-0021-0352 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-353 | PID | 353 | 082623C-2000-PID-0021-0353 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-354 | PID | 354 | 082623C-2000-PID-0021-0354 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-355 | PID | 355 | 082623C-2000-PID-0021-0355 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-356 | PID | 356 | 082623C-2000-PID-0021-0356 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-357 | PID | 357 | 082623C-2000-PID-0021-0357 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-358 | PID | 358 | 082623C-2000-PID-0021-0358 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-359 | PID | 359 | 082623C-2000-PID-0021-0359 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-360 | PID | 360 | 082623C-2000-PID-0021-0360 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-361 | PID | 361 | 082623C-2000-PID-0021-0361 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-362 | PID | 362 | 082623C-2000-PID-0021-0362 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-363 | PID | 363 | 082623C-2000-PID-0021-0363 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-364 | PID | 364 | 082623C-2000-PID-0021-0364 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-365 | PID | 365 | 082623C-2000-PID-0021-0365 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-366 | PID | 366 | 082623C-2000-PID-0021-0366 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-367 | PID | 367 | 082623C-2000-PID-0021-0367 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-368 | PID | 368 | 082623C-2000-PID-0021-0368 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-369 | PID | 369 | 082623C-2000-PID-0021-0369 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-370 | PID | 370 | 082623C-2000-PID-0021-0370 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-371 | PID | 371 | 082623C-2000-PID-0021-0371 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-372 | PID | 372 | 082623C-2000-PID-0021-0372 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-373 | PID | 373 | 082623C-2000-PID-0021-0373 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-374 | PID | 374 | 082623C-2000-PID-0021-0374 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-375 | PID | 375 | 082623C-2000-PID-0021-0375 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-376 | PID | 376 | 082623C-2000-PID-0021-0376 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-377 | PID | 377 | 082623C-2000-PID-0021-0377 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-378 | PID | 378 | 082623C-2000-PID-0021-0378 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-379 | PID | 379 | 082623C-2000-PID-0021-0379 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-380 | PID | 380 | 082623C-2000-PID-0021-0380 | 0 | B | IFA | PROCESS PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-381 | PID | 381 | 082623C-2000-PID-0021-0381 | 0 | B | IFA | UTILITIES PID - STEAM CRACKER UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-PID-382 | PID | 382 | 082623C-2000-PID-1931-0001 | 0 | B | IFA | FIRE PROTECTION PIDS (NETWORK AND DISTRIBUTION) | 2020-12-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-RPT-001 | RPT | 1 | 082623C-2000-CN-0008-0004 | 0 | B | IFA | MATERIAL SELECTION REPORT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-RPT-002 | RPT | 2 | 082623C-2000-CN-0008-0002 | 0 | B | IFA | FLARE DESIGN REPORT (INCL FLARE LOAD MITIGATION PHILOSOPHY) | 2020-12-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-SUM-001 | SUM | 1 | 082623C-2000-EL-0101 | 0 | B | IFA | PROCESS SIZED EQUIPMENT SUMMARY - STEAM CRACKER | 2020-11-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-SUM-002 | SUM | 2 | 082623C-2000-NM-0003-0001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - STEAM CRACKER | 2020-12-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-SUM-003 | SUM | 3 | 082623C-2000-NM-0004-0001 | 0 | B | IFA | CATALYST AND CHEMICALS CONSUMPTION SUMMARY - STEAM CRACKER | 2020-12-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-SUM-004 | SUM | 4 | 082623C-2000-NM-0005-0001 | 0 | B | IFA | EFFLUENT SUMMARY - STEAM CRACKER | 2020-11-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2000 | A8RX-TSC-2000-225-SUM-005 | SUM | 5 | 082623C-2000-NM-0014-0001 | 0 | B | IFA | RELIEF LOAD SUMMARY- STEAM CRACKER | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 2000 | A8RX-TSC-2000-250-PLN-001 | PLN | 1 | 082623C-2000-DW-0051-0003 | 0 | B | IFA | UNIT PLOT-PLANS STEAM CRACKER | 2020-10-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 2000 | A8RX-TSC-2000-250-PLN-002 | PLN | 2 | 082623C-2000-DW-0053-0003 | 0 | B | IFA | KEY PLOT-PLANS STEAM CRACKER | 2020-10-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 2000 | A8RX-TSC-2000-255-DST-200 | DST | 200 | 082623C-2000-SP-0410-0001 | 0 | B | IFA | MECHANICAL DATA SHEET FOR CRACKED GAS DRYERS (FF-2250 A/B) | 2020-11-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 2000 | A8RX-TSC-2000-255-DST-201 | DST | 201 | 082623C-2000-SP-0410-0002 | 0 | B | IFA | MECHANICAL DATA SHEET FOR C2 HYDROGENATOR REACTORS (DC-2280 A/B/C) | 2020-11-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 2000 | A8RX-TSC-2000-255-DST-202 | DST | 202 | 082623C-2000-SP-0410-0003 | 0 | B | IFA | MECHANICAL DATA SHEET FOR C3 HYDROGENATOR REACTORS (DC-2360 A/B) | 2020-11-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 2000 | A8RX-TSC-2000-255-DST-203 | DST | 203 | 082623C-2000-SP-0510-0001 | 0 | B | IFA | MECHANICAL DATA SHEET FOR QUENCH OIL TOWER (DD-2110) | 2020-11-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 2000 | A8RX-TSC-2000-255-DST-204 | DST | 204 | 082623C-2000-SP-0510-0002 | 0 | B | IFA | MECHANICAL DATA SHEET FOR QUENCH WATER TOWER (DD-2120) | 2020-11-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 2000 | A8RX-TSC-2000-255-DST-205 | DST | 205 | 082623C-2000-SP-0510-0003 | 0 | B | IFA | MECHANICAL DATA SHEET FOR DEMETHANIZER (DD-2330) | 2020-11-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 2000 | A8RX-TSC-2000-255-DST-206 | DST | 206 | 082623C-2000-SP-0510-0004 | 0 | B | IFA | MECHANICAL DATA SHEET FOR C2 SPLITTER (DD-2350) | 2020-11-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 2000 | A8RX-TSC-2000-255-DST-207 | DST | 207 | 082623C-2000-SP-0510-0005 | 0 | B | IFA | MECHANICAL DATA SHEET FOR C3 SPLITTER (DD-2370) | 2020-11-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 2000 | A8RX-TSC-2000-255-SPC-500 | SPC | 500 | 082623C-2000-SP-1011-0001 | 0 | B | IFA | SP CENTRIFUGAL COMPRESSORS | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 2000 | A8RX-TSC-2000-255-SPC-501 | SPC | 501 | 082623C-2000-SP-1011-0002 | 0 | B | IFA | SP CENTRIFUGAL COMPRESSORS | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 2000 | A8RX-TSC-2000-255-SPC-502 | SPC | 502 | 082623C-2000-SP-1011-0003 | 0 | B | IFA | SP CENTRIFUGAL COMPRESSORS | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 2000 | A8RX-TSC-2000-265-DWG-001 | DWG | 1 | 082623C-2000-DW-1622-0001 | 0 | B | IFA | ELECTRICAL MAIN CABLE ROUTING STEAM CRAKER | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 2000 | A8RX-TSC-2000-265-HAC-001 | HAC | 1 | 082623C-2000-DW-1920-0001 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION STEAM CRAKER | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 2000 | A8RX-TSC-2000-265-LST-001 | LST | 1 | 082623C-2000-NM-1601-0001 | 0 | B | IFA | ELECTRICAL LOAD LIST - STEAM CRACKER | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 2000 | A8RX-TSC-2000-270-DWG-001 | DWG | 1 | 082623C-2000-DW-1572-0001 | 0 | B | IFA | INSTRUMENT MAIN CABLE ROUTING STEAM CRACKER | 2021-01-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 2000 | A8RX-TSC-2000-500-IOM-001 | IOM | 1 | 082623C-2000-ML-0901-0001 | 0 | B | IFI | SUPERVISORY OPERATING MANUAL - STEAM CRACKER | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-FHA-001 | FHA | 1 | 082623C-2000-RT-1900-0201 | 0 | B | IFI | HAZID REPORT | 2020-10-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-001 | LAY | 1 | 082623C-2000-DW-1933-0101 | 0 | B | IFA | FIRE FIGHTING LAYOUT (SCU) | 2020-11-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-002 | LAY | 2 | 082623C-2000-DW-1933-0102 | 0 | B | IFA | FIRE FIGHTING LAYOUT (SCU) | 2020-11-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-003 | LAY | 3 | 082623C-2000-DW-1933-0103 | 0 | B | IFA | FIRE FIGHTING LAYOUT (SCU) | 2020-11-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-004 | LAY | 4 | 082623C-2000-DW-1933-0104 | 0 | B | IFA | FIRE FIGHTING LAYOUT (SCU) | 2020-11-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-005 | LAY | 5 | 082623C-2000-DW-1933-0105 | 0 | B | IFA | FIRE FIGHTING LAYOUT (SCU) | 2020-11-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-006 | LAY | 6 | 082623C-2000-DW-1933-0201 | 0 | B | IFA | SAFETY AND PORTABLE FIRE EQUIPMENT LAYOUT (SCU) | 2020-11-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-007 | LAY | 7 | 082623C-2000-DW-1933-0202 | 0 | B | IFA | SAFETY AND PORTABLE FIRE EQUIPMENT LAYOUT (SCU) | 2020-11-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-008 | LAY | 8 | 082623C-2000-DW-1933-0203 | 0 | B | IFA | SAFETY AND PORTABLE FIRE EQUIPMENT LAYOUT (SCU) | 2020-11-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-009 | LAY | 9 | 082623C-2000-DW-1933-0204 | 0 | B | IFA | SAFETY AND PORTABLE FIRE EQUIPMENT LAYOUT (SCU) | 2020-11-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-010 | LAY | 10 | 082623C-2000-DW-1933-0205 | 0 | B | IFA | SAFETY AND PORTABLE FIRE EQUIPMENT LAYOUT (SCU) | 2020-11-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-011 | LAY | 11 | 082623C-2000-DW-1950-0001 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-012 | LAY | 12 | 082623C-2000-DW-1950-0002 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-013 | LAY | 13 | 082623C-2000-DW-1950-0003 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-014 | LAY | 14 | 082623C-2000-DW-1950-0004 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-015 | LAY | 15 | 082623C-2000-DW-1950-0005 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-016 | LAY | 16 | 082623C-2000-DW-1980-0001 | 0 | B | IFA | PASSIVE FIRE PROTECTION ZONE LAYOUT - (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-017 | LAY | 17 | 082623C-2000-DW-1980-0002 | 0 | B | IFA | PASSIVE FIRE PROTECTION ZONE LAYOUT - (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-018 | LAY | 18 | 082623C-2000-DW-1980-0003 | 0 | B | IFA | PASSIVE FIRE PROTECTION ZONE LAYOUT - (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-019 | LAY | 19 | 082623C-2000-DW-1980-0004 | 0 | B | IFA | PASSIVE FIRE PROTECTION ZONE LAYOUT - (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LAY-020 | LAY | 20 | 082623C-2000-DW-1980-0005 | 0 | B | IFA | PASSIVE FIRE PROTECTION ZONE LAYOUT - (SCU) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-LST-001 | LST | 1 | 082623C-2000-CN-1901-0003 | 0 | B | IFI | MSDS COLLECTION | 2021-01-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-PHA-001 | PHA | 1 | 082623C-2000-RT-1990-0201 | 0 | C | IFI | HAZOP STUDY REPORT (TEAM 1 - SCU) | 2021-03-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 2000 | A8RX-TSC-2000-653-PHA-002 | PHA | 2 | 082623C-2000-RT-1990-5000 | 0 | C | IFI | LOPA (SIL CLASSIFICATION) REPORT (SCU) | 2021-03-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 2100 | A8RX-TSC-2100-210-PLN-001 | PLN | 1 | 082623C002-DW-1721-001 | 0 | B | IFA | DRAWINGS - FOUNDATION LOCATION PLAN - CONCEPTUAL DESIGN - FURNACES | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 2100 | A8RX-TSC-2100-210-PLN-002 | PLN | 2 | 082623C002-DW-1721-002 | 0 | B | IFA | DRAWINGS - FOUNDATION LOCATION PLAN - CONCEPTUAL DESIGN - DMDS | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 2100 | A8RX-TSC-2100-210-PLN-003 | PLN | 3 | 082623C002-DW-1721-003 | 0 | B | IFA | DRAWINGS - FOUNDATION LOCATION PLAN - CONCEPTUAL DESIGN - DECOKE AIR COMPRESSOR | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 215 | STRUCTURAL | 2100 | A8RX-TSC-2100-215-DWG-001 | DWG | 1 | 082623C002-DW-1821-001 | 0 | B | IFA | DRAWINGS - STEEL VALVE PLATFORM STRUCTURE - CONCEPTUAL DESIGN - FURNACE | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-CAE-001 | CAE | 1 | 082623C-2100-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 2100 (CRACKING FURNACES) | 2021-01-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-CAE-002 | CAE | 2 | 082623C-2100-NM-0013-0002 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 2100 (HOT SECTION) | 2021-01-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-CAE-003 | CAE | 3 | 082623C002-NM-0013-001 | 0 | B | IFA | CAUSE AND EFFECT DIAGRAM | 2020-11-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-DBD-001 | DBD | 1 | 082623C002-JSD-0000-003 | 0 | B | IFA | PROCESS BASIS OF DESIGN- STEAM CRACKING FURNACES | 2020-09-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-DST-001 | DST | 1 | 082623C002-PDS-1545-001 | 0 | B | IFI | PROCESS DATA SHEET - RELIEF VALVES | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-DST-002 | DST | 2 | 082623C002-PDS-1541-001 | 0 | B | IFI | PROCESS DATA - CONTROL VALVES | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-DST-003 | DST | 3 | 082623C002-PDS-1560-001 | 0 | B | IFI | PROCESS DATA - ANALYSERS | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-LST-001 | LST | 1 | 082623C002-EL-0102 | 0 | B | IFA | SIZED EQUIPMENT LIST | 2020-11-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-LST-002 | LST | 2 | 082623C002-NM-0005-001 | 0 | B | IFA | EFFLUENT LIST | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-MSD-001 | MSD | 1 | 082623C002-MSD-0010-112 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - FURNACES OVERVIEW | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-MSD-002 | MSD | 2 | 082623C002-MSD-0010-113 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - GK6 FURNACE | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-MSD-003 | MSD | 3 | 082623C002-MSD-0010-114 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - SMK FURNACE | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-MSD-004 | MSD | 4 | 082623C002-MSD-0010-115 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - DMDS AND AMMONIA DOSING | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-NAR-001 | NAR | 1 | 082623C002-JSD-0000-004 | 0 | B | IFA | PROCESS DESCRIPTION - STEAM CRACKING FURNACES | 2020-09-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-NAR-002 | NAR | 2 | 082623C-2100-CN-0008-0001 | 0 | B | IFI | CONTROL NARRATIVES - COMPLEX LOOPS - CRACKING FURNACES | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-NAR-003 | NAR | 3 | 082623C002-JSS-0013-002 | 0 | B | IFI | PROCESS SAFEGUARDING DESCRIPTION | 2020-11-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-NAR-004 | NAR | 4 | 082623C002-ML-0000-001 | 0 | B | IFI | D/O MANUAL | 2021-01-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-NAR-005 | NAR | 5 | 082623C002-JSS-0013-001 | 0 | B | IFI | PROCESS CONTROL DESCRIPTION | 2020-11-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2000-225-PFD-112 | PFD | 112 | 082623C-2000-PFD-0010-0112 | 0 | B | IFA | PROCESS FLOW DIAGRAM - FURNACES OVERVIEW | 2020-09-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2000-225-PFD-113 | PFD | 113 | 082623C-2000-PFD-0010-0113 | 0 | B | IFA | PROCESS FLOW DIAGRAM - GK6 FURNACE | 2020-09-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2000-225-PFD-114 | PFD | 114 | 082623C-2000-PFD-0010-0114 | 0 | B | IFA | PROCESS FLOW DIAGRAM - SMK FURNACE | 2020-09-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2000-225-PFD-115 | PFD | 115 | 082623C-2000-PFD-0010-0115 | 0 | B | IFA | PROCESS FLOW DIAGRAM - DMDS AND AMMONIA DOSING | 2020-09-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2000-225-PFD-116 | PFD | 116 | 082623C-2000-PFD-0010-0116 | 0 | B | IFA | PROCESS FLOW DIAGRAM - DECOKE AIR COMPRESSOR AND DECOKE CYCLONE | 2020-09-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-PID-001 | PID | 1 | 082623C002-PID-0021-120 | 0 | B | IFA | PID DOCUMENT SET - CRACKING FURNACES | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-SUM-001 | SUM | 1 | 082623C002-NM-0003-001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY | 2020-10-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2100 | A8RX-TSC-2100-225-SUM-002 | SUM | 2 | 082623C002-NM-0004-001 | 0 | B | IFA | CHEMICALS SUMMARY | 2020-10-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 2100 | A8RX-TSC-2100-250-LST-001 | LST | 1 | 082623C002-NM-1350-002 | 0 | B | IFA | PIPING INTERFACE BL LIST FOR FURNACES | 2020-12-17 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 2100 | A8RX-TSC-2100-250-PLN-001 | PLN | 1 | 082623C002-DW-0051-001 | 0 | B | IFA | PLOTPLAN FOR FURNACES | 2020-10-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 2100 | A8RX-TSC-2100-250-SPC-001 | SPC | 1 | 082623C002-SP-0137-001 | 0 | B | IFI | TECHNICAL SPECIFICATION FOR CRACKED GAS AND DECOKE VALVES FOR FURNACE | 2020-11-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 2100 | A8RX-TSC-2100-250-SPC-002 | SPC | 2 | 082623C002-JSS-1310-001 | 0 | B | IFI | TECHNICAL SPECIFICATION FOR CRACKED GAS AND DECOKE VALVES FOR FURNACE | 2020-11-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 2100 | A8RX-TSC-2100-250-SPC-003 | SPC | 3 | 082623C002-JSD-1300-010 | 0 | B | IFI | GENERAL DESIGN RULES FOR PIPING SUPPORTS FOR FURNACES | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 2100 | A8RX-TSC-2100-250-SPC-004 | SPC | 4 | 082623C002-JSS-1310-007 | 0 | B | IFI | TECHNICAL SPECIFICATION FOR CRACKED GAS AND DECOKE VALVES FOR FURNACE | 2020-11-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-HEATERS & BOILERS | 2100 | A8RX-TSC-2100-255-DWG-001 | DWG | 1 | 082623C002-DW-0131-004 | 0 | B | IFI | GENERAL ARRANGEMENT 2D STUDY DRAWING FURNACE | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-HEATERS & BOILERS | 2100 | A8RX-TSC-2100-255-DWG-002 | DWG | 2 | 082623C002-DW-0131-010 | 0 | B | IFI | DRAWINGS - PRELIMINARY FOUNDATION PLAN FURNACE | 2020-11-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-HEATERS & BOILERS | 2100 | A8RX-TSC-2100-255-SPC-001 | SPC | 1 | 082623C002-JSD-0117-001 | 0 | B | IFI | MECHANICAL BASIS OF DESIGN CRACKING FURNACE | 2020-09-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-HEATERS & BOILERS | 2100 | A8RX-TSC-2100-255-STD-001 | STD | 1 | 082623C002-STD-0117-001 | 0 | B | IFI | DESIGN STANDARD - EXAMPLE DRAWINGS CRACKING FURNACE STEEL | 2020-10-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 2100 | A8RX-TSC-2100-265-DWG-001 | DWG | 1 | 082623C002-DW-1622-000 | 0 | B | IFI | ELECTRICAL MAIN CABLE ROUTING | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 2100 | A8RX-TSC-2100-265-HAC-001 | HAC | 1 | 082623C002-DW-1920-001 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION LAY OUT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 2100 | A8RX-TSC-2100-265-LST-001 | LST | 1 | 082623C002-NM-1601-001 | 0 | B | IFA | ELECTRICAL LOAD LIST | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 2100 | A8RX-TSC-2100-265-SLD-001 | SLD | 1 | 082623C002-DW-1652-001 | 0 | B | IFA | KEY SINGLE LINE DIAGRAM | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 2100 | A8RX-TSC-2100-270-LST-001 | LST | 1 | 082623C-2100-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST FURNANCE AND HOT SECTION | 2020-12-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2200 | A8RX-TSC-2200-225-CAE-001 | CAE | 1 | 082623C-2200-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 2200 | 2021-01-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 2200 | A8RX-TSC-2200-270-LST-001 | LST | 1 | 082623C-2200-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST CGC, CT AND CGD SECTION | 2020-12-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2300 | A8RX-TSC-2300-225-CAE-001 | CAE | 1 | 082623C-2300-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 2300 | 2021-01-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 2300 | A8RX-TSC-2300-270-LST-001 | LST | 1 | 082623C-2300-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST COLD BOX AND PURIFICATION SECTION | 2020-12-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2400 | A8RX-TSC-2400-225-CAE-001 | CAE | 1 | 082623C-2400-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 2400 | 2021-01-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 2400 | A8RX-TSC-2400-270-LST-001 | LST | 1 | 082623C-2400-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST REFRIGERANT COMPRESSOR SECTION | 2020-12-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2500 | A8RX-TSC-2500-225-CAE-001 | CAE | 1 | 082623C-2500-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 2500 | 2021-01-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 2500 | A8RX-TSC-2500-270-LST-001 | LST | 1 | 082623C-2500-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST GAS RELATED SC UTILITIES | 2020-12-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2600 | A8RX-TSC-2600-225-CAE-001 | CAE | 1 | 082623C-2600-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 2600 | 2021-01-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 2600 | A8RX-TSC-2600-270-LST-001 | LST | 1 | 082623C-2600-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST WATER RELATED SC UTILITIES | 2020-12-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2700 | A8RX-TSC-2700-225-CAE-001 | CAE | 1 | 082623C-2700-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 2700 | 2021-01-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 2700 | A8RX-TSC-2700-270-LST-001 | LST | 1 | 082623C-2700-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST PSA SUB-UNIT | 2020-12-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 2800 | A8RX-TSC-2800-225-CAE-001 | CAE | 1 | 082623C-2800-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 2800 | 2021-01-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3000 | A8RX-TSC-3000-225-PID-001 | PID | 1 | 082623C-3000-PID-1931-0001 | 0 | B | IFA | FIRE PROTECTION PIDS (NETWORK AND DISTRIBUTION) | 2020-12-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 3000 | A8RX-TSC-3000-255-DST-200 | DST | 200 | 082623C-3000-SP-0410-0004 | 0 | B | IFA | MECHANICAL DATA SHEET FOR HYDROGENATION REACTOR 2ND STAGE | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 3000 | A8RX-TSC-3000-255-SPC-500 | SPC | 500 | 082623C-3000-SP-1011-0001 | 0 | B | IFA | SP CENTRIFUGAL COMPRESSORS | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 3000 | A8RX-TSC-3000-265-DWG-001 | DWG | 1 | 082623C-3000-DW-1622-0001 | 0 | B | IFA | ELECTRICAL MAIN CABLE ROUTING SE-PHG | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3000 | A8RX-TSC-3000-653-PHA-001 | PHA | 1 | 082623C-3000-RT-1990-0201 | 0 | C | IFI | HAZOP STUDY REPORT (TEAM 2 - PERIPHERAL UNITS + SG) | 2021-03-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3000 | A8RX-TSC-3000-653-PHA-002 | PHA | 2 | 082623C-3000-RT-1990-5000 | 0 | C | IFI | LOPA (SIL CLASSIFICATION) REPORT (PERIPHERAL UNITS + SG) | 2021-03-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-CAE-001 | CAE | 1 | 3200-ZA-D-71101 | 0 | B | IFA | CAUSE AND EFFECT DIAGRAMS - ETBE | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-DBD-001 | DBD | 1 | 3200-ZA-E-70004 | 0 | B | IFA | PROCESS DESIGN BASIS - ETBE UNIT | 2020-10-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-DST-001 | DST | 1 | 3200-ZA-D-71003 | 0 | B | IFA | DATA SHEET FOR CRITICAL PSV ETBE UNIT | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-DST-002 | DST | 2 | 3200-ZA-D-71002 | 0 | B | IFA | DATA SHEET FOR CRITICAL CONTROL VALVE ETBE UNIT | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-DST-003 | DST | 3 | 3200-ZA-D-71004 | 0 | B | IFA | DATA SHEET FOR ANALYZER ETBE UNIT | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-MSD-001 | MSD | 1 | 3200-GD-B-75250 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM ETBE N°1 | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-MSD-002 | MSD | 2 | 3200-GD-B-75251 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM ETBE N°2 | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-MSD-003 | MSD | 3 | 3200-GD-B-75252 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM ETBE N°3 | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-MSD-004 | MSD | 4 | 3200-GD-B-75253 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM ETBE N°4 | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-MSD-005 | MSD | 5 | 3200-GD-B-75254 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM ETBE N°5 | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-MSD-006 | MSD | 6 | 3200-GD-B-75255 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM ETBE N°6 | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-MSD-007 | MSD | 7 | 3200-GD-B-75256 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM CONCENTRATION UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-NAR-001 | NAR | 1 | 3200-ZA-E-70005 | 0 | B | IFA | PROCESS DESCRIPTION - ETBE UNIT | 2021-02-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-NAR-002 | NAR | 2 | 3200-ZA-E-71102 | 0 | B | IFA | CONTROL NARRATIVES FOR COMPLEX LOOPS - ETBE | 2021-02-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-NAR-003 | NAR | 3 | 3200-ZA-E-70017 | 0 | B | IFI | SUPERVISORY OPERATING MANUAL - ETBE | 2021-03-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PFD-001 | PFD | 1 | 3200-GD-B-75050 | 0 | B | IFA | PROCESS FLOW DIAGRAM ETBE N°1 | 2020-10-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PFD-002 | PFD | 2 | 3200-GD-B-75051 | 0 | B | IFA | PROCESS FLOW DIAGRAM ETBE N°2 | 2020-10-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PFD-003 | PFD | 3 | 3200-GD-B-75052 | 0 | B | IFA | PROCESS FLOW DIAGRAM ETBE N°3 | 2020-10-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PFD-004 | PFD | 4 | 3200-GD-B-75053 | 0 | B | IFA | PROCESS FLOW DIAGRAM ETBE N°4 | 2020-10-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PFD-005 | PFD | 5 | 3200-GD-B-75054 | 0 | B | IFA | PROCESS FLOW DIAGRAM ETBE N°5 | 2020-10-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PFD-006 | PFD | 6 | 3200-GD-B-75055 | 0 | B | IFA | PROCESS FLOW DIAGRAM ETBE N°6 | 2020-10-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PFD-007 | PFD | 7 | 3200-GD-B-75056 | 0 | B | IFA | PROCESS FLOW DIAGRAM ETBE N°7 | 2020-10-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PFD-008 | PFD | 8 | 3200-GD-B-75057 | 0 | B | IFA | PROCESS FLOW DIAGRAM CONCENTRATION UNIT | 2020-10-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-001 | PID | 1 | 3200-GD-B-76300 | 0 | B | IFA | PROCESS PID ETBE N° 1 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-002 | PID | 2 | 3200-GD-B-76301 | 0 | B | IFA | PROCESS PID ETBE N° 2 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-003 | PID | 3 | 3200-GD-B-76302 | 0 | B | IFA | PROCESS PID ETBE N° 3 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-004 | PID | 4 | 3200-GD-B-76303 | 0 | B | IFA | PROCESS PID ETBE N° 4 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-005 | PID | 5 | 3200-GD-B-76304 | 0 | B | IFA | PROCESS PID ETBE N° 5 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-006 | PID | 6 | 3200-GD-B-76305 | 0 | B | IFA | PROCESS PID ETBE N° 6 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-007 | PID | 7 | 3200-GD-B-76306 | 0 | B | IFA | PROCESS PID ETBE N° 7 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-008 | PID | 8 | 3200-GD-B-76307 | 0 | B | IFA | PROCESS PID ETBE N° 8 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-009 | PID | 9 | 3200-GD-B-76308 | 0 | B | IFA | PROCESS PID ETBE N° 9 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-010 | PID | 10 | 3200-GD-B-76309 | 0 | B | IFA | PROCESS PID ETBE N° 10 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-011 | PID | 11 | 3200-GD-B-76310 | 0 | B | IFA | PROCESS PID ETBE N° 11 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-012 | PID | 12 | 3200-GD-B-76311 | 0 | B | IFA | PROCESS PID ETBE N° 12 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-013 | PID | 13 | 3200-GD-B-76312 | 0 | B | IFA | PROCESS PID ETBE N° 13 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-014 | PID | 14 | 3200-GD-B-76313 | 0 | B | IFA | PROCESS PID ETBE N° 14 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-015 | PID | 15 | 3200-GD-B-76314 | 0 | B | IFA | PROCESS PID ETBE N° 15 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-016 | PID | 16 | 3200-GD-B-76315 | 0 | B | IFA | PROCESS PID ETBE N° 16 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-017 | PID | 17 | 3200-GD-B-76316 | 0 | B | IFA | PROCESS PID ETBE N° 17 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-018 | PID | 18 | 3200-GD-B-76317 | 0 | B | IFA | PROCESS PID ETBE N° 18 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-019 | PID | 19 | 3200-GD-B-76318 | 0 | B | IFA | PROCESS PID ETBE N° 19 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-020 | PID | 20 | 3200-GD-B-76319 | 0 | B | IFA | PROCESS PID ETBE N° 20 | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-021 | PID | 21 | 3200-GD-B-76400 | 0 | B | IFA | PROCESS PID ETBE DISTRIBUTION NITROGEN AND IA/UA | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-022 | PID | 22 | 3200-GD-B-76401 | 0 | B | IFA | PROCESS PID ETBE DISTRIBUTION STEAM | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-023 | PID | 23 | 3200-GD-B-76402 | 0 | B | IFA | PROCESS PID ETBE DISTRIBUTION CONDENSATE | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-024 | PID | 24 | 3200-GD-B-76403 | 0 | B | IFA | PROCESS PID ETBE DISTRIBUTION COOLING WATER | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-025 | PID | 25 | 3200-GD-B-76404 | 0 | B | IFA | PROCESS PID ETBE DISTRIBUTION FLARE | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-PID-026 | PID | 26 | 3200-GD-B-76405 | 0 | B | IFA | PROCESS PID ETBE DISTRIBUTION WATERS | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-RPT-001 | RPT | 1 | 3200-ZA-D-70018 | 0 | B | IFA | MATERIAL SELECTION REPORT - ETBE UNIT | 2021-01-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-RPT-002 | RPT | 2 | 3200-ZA-E-70007 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - ETBE | 2020-10-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-SUM-001 | SUM | 1 | 3200-ZA-E-70025 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - ETBE | 2021-02-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-SUM-002 | SUM | 2 | 3200-ZA-E-70028 | 0 | B | IFA | EFFLUENT SUMMARY - ETBE | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-SUM-003 | SUM | 3 | 3200-ZA-E-70030 | 0 | B | IFA | PROCESS SIZED EQUIPMENT SUMMARY - ETBE | 2020-11-19 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-SUM-004 | SUM | 4 | 3200-ZA-E-70033 | 0 | B | IFA | RELIEF LOAD SUMMARY - ETBE | 2021-02-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3200 | A8RX-TSC-3200-225-SUM-005 | SUM | 5 | 3200-ZA-E-70015 | 0 | B | IFA | CATALYST AND CHEMICAL SUMMARY ETBE UNIT | 2020-12-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 3200 | A8RX-TSC-3200-250-LAY-001 | LAY | 1 | 3200-GB-B-65110 | 0 | B | IFA | ETBE AREA - UNIT PLOT PLAN | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 3200 | A8RX-TSC-3200-255-SUM-501 | SUM | 501 | 3200-MA-E-30013 | 0 | B | IFA | EQUIPMENT SUMMARY FOR UNIT 3200 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 3200 | A8RX-TSC-3200-265-LAY-001 | LAY | 1 | 3200-EB-A-40044 | 0 | B | IFA | ELECTRICAL AND INSTRUMENT ETBE UNIT CABLE ROUTING | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 3200 | A8RX-TSC-3200-265-SLD-001 | SLD | 1 | 3200-EC-B-40014 | 0 | B | IFA | KEY SINGLE LINE DIAGRAM ETBE UNIT SUBSTATION | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 3200 | A8RX-TSC-3200-270-DTA-001 | DTA | 1 | 3200-SA-E-50013 | 0 | B | IFA | INSTRUMENT INDEX FOR ETBE - UNIT 3200 | 2020-12-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3200 | A8RX-TSC-3200-653-DST-001 | DST | 1 | 3200-ZX-E-80011 | 0 | B | IFI | MSDS COMPILATION - ETBE UNIT | 2021-02-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3200 | A8RX-TSC-3200-653-HAC-001 | HAC | 1 | 3200-ZB-B-85011 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION LAYOUT - ETBE AREA | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3200 | A8RX-TSC-3200-653-LAY-001 | LAY | 1 | 3200-ZB-B-85005 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT - ETBE AREA | 2021-01-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3200 | A8RX-TSC-3200-653-LAY-002 | LAY | 2 | 3200-ZB-B-85008 | 0 | B | IFA | FIREPROOFING ZONE LAYOUT - ETBE AREA | 2021-01-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3200 | A8RX-TSC-3200-653-LAY-003 | LAY | 3 | 3200-ZB-A-85020 | 0 | B | IFA | FIREWATER DISTRIBUTION LAYOUT - ETBE AREA | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 3300 | A8RX-TSC-3300-210-DWG-001 | DWG | 1 | 082623C-3300-DW-1442-0001 | 0 | B | IFA | MAJOR UNDERGROUND STIRENE | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-CAE-001 | CAE | 1 | 082623C-3300-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 3300 | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-DBD-001 | DBD | 1 | 082623C-3300-CN-0007-0001 | 0 | B | IFA | PROCESS DESIGN BASIS - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-DBD-002 | DBD | 2 | 082623C-3300-NM-0001-0001 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - STYRENE EXTRACTION UNIT (SUMMER CASE) | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-DBD-003 | DBD | 3 | 082623C-3300-NM-0001-0002 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - STYRENE EXTRACTION UNIT (WINTER CASE) | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-DST-001 | DST | 1 | 082623C-3300-SP-1500-0045 | 0 | B | IFI | DS FOR SAFETY MATL (PSV, TRV, BREATHER VALVES) - STYRENE EXTRACTION UNIT | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-DST-002 | DST | 2 | 082623C-3300-SP-1500-0041 | 0 | B | IFI | DS FOR CRITICAL CONTROL VALVES - STYRENE EXTRACTION UNIT | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-DST-003 | DST | 3 | 082623C-3300-SP-1500-0001 | 0 | B | IFI | DS FOR ANALYZERS - STYRENE EXTRACTION UNIT | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-NAR-001 | NAR | 1 | 082623C-3300-CN-0009-0001 | 0 | B | IFA | PROCESS DESCRIPTION - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PFD-001 | PFD | 1 | 082623C-3300-PFD-0010-0001 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PFD-002 | PFD | 2 | 082623C-3300-PFD-0010-0002 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PFD-003 | PFD | 3 | 082623C-3300-PFD-0010-0003 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PFD-004 | PFD | 4 | 082623C-3300-PFD-0010-0004 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PFD-005 | PFD | 5 | 082623C-3300-PFD-0010-0005 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PFD-006 | PFD | 6 | 082623C-3300-PFD-0010-0006 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PFD-007 | PFD | 7 | 082623C-3300-PFD-0010-0007 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PFD-008 | PFD | 8 | 082623C-3300-PFD-0010-0008 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-10-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-001 | PID | 1 | 082623C-3300-PID-0021-0001 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-002 | PID | 2 | 082623C-3300-PID-0021-0002 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-003 | PID | 3 | 082623C-3300-PID-0021-0003 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-004 | PID | 4 | 082623C-3300-PID-0021-0004 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-005 | PID | 5 | 082623C-3300-PID-0021-0005 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-006 | PID | 6 | 082623C-3300-PID-0021-0006 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-007 | PID | 7 | 082623C-3300-PID-0021-0007 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-008 | PID | 8 | 082623C-3300-PID-0021-0008 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-009 | PID | 9 | 082623C-3300-PID-0021-0009 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-010 | PID | 10 | 082623C-3300-PID-0021-0010 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-011 | PID | 11 | 082623C-3300-PID-0021-0011 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-012 | PID | 12 | 082623C-3300-PID-0021-0012 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-013 | PID | 13 | 082623C-3300-PID-0021-0013 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-014 | PID | 14 | 082623C-3300-PID-0021-0014 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-015 | PID | 15 | 082623C-3300-PID-0021-0015 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-016 | PID | 16 | 082623C-3300-PID-0021-0016 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-017 | PID | 17 | 082623C-3300-PID-0021-0017 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-018 | PID | 18 | 082623C-3300-PID-0021-0018 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-019 | PID | 19 | 082623C-3300-PID-0021-0019 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-020 | PID | 20 | 082623C-3300-PID-0021-0020 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-021 | PID | 21 | 082623C-3300-PID-0021-0021 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-022 | PID | 22 | 082623C-3300-PID-0021-0022 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-023 | PID | 23 | 082623C-3300-PID-0021-0023 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-024 | PID | 24 | 082623C-3300-PID-0021-0024 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-025 | PID | 25 | 082623C-3300-PID-0021-0025 | 0 | B | IFA | PROCESS PID - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-026 | PID | 26 | 082623C-3300-PID-0031-0001 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-027 | PID | 27 | 082623C-3300-PID-0031-0002 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-028 | PID | 28 | 082623C-3300-PID-0031-0003 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-029 | PID | 29 | 082623C-3300-PID-0031-0004 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-030 | PID | 30 | 082623C-3300-PID-0031-0005 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-031 | PID | 31 | 082623C-3300-PID-0031-0006 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-032 | PID | 32 | 082623C-3300-PID-0031-0007 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-033 | PID | 33 | 082623C-3300-PID-0031-0008 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-034 | PID | 34 | 082623C-3300-PID-0031-0009 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-PID-035 | PID | 35 | 082623C-3300-PID-0031-0010 | 0 | B | IFA | UTILITIES DIAGRAMS - STYRENE EXTRACTION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-SUM-001 | SUM | 1 | 082623C-3300-EL-0101 | 0 | B | IFA | PROCESS SIZED EQUIPMENT SUMMARY - STYRENE EXTRACTION UNIT | 2020-11-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-SUM-002 | SUM | 2 | 082623C-3300-NM-0003-0001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - STYRENE EXTRACTION UNIT | 2021-01-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-SUM-003 | SUM | 3 | 082623C-3300-NM-0004-0001 | 0 | B | IFA | CATALYST AND CHEMICALS CONSUMPTION SUMMARY - STYRENE EXTRACTION UNIT | 2020-11-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-SUM-004 | SUM | 4 | 082623C-3300-NM-0005-0001 | 0 | B | IFA | EFFLUENT SUMMARY - STYRENE EXTRACTION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3300 | A8RX-TSC-3300-225-SUM-005 | SUM | 5 | 082623C-3300-NM-0014-0001 | 0 | B | IFA | RELIEF LOAD SUMMARY - STYRENE EXTRACTION UNIT | 2020-11-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 3300 | A8RX-TSC-3300-250-PLN-001 | PLN | 1 | 082623C-3300-DW-0051-0003 | 0 | B | IFA | UNIT PLOT-PLANS STYRENE EXTRACTION | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 3300 | A8RX-TSC-3300-250-PLN-002 | PLN | 2 | 082623C-3300-DW-0053-0003 | 0 | B | IFA | KEY PLOT-PLANS STYRENE EXTRACTION | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 3300 | A8RX-TSC-3300-265-HAC-001 | HAC | 1 | 082623C-3300-DW-1920-0001 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION SE | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 3300 | A8RX-TSC-3300-265-LST-001 | LST | 1 | 082623C-3300-NM-1601-0001 | 0 | B | IFA | ELECTRICAL LOAD LIST - STYRENE | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 3300 | A8RX-TSC-3300-270-DWG-001 | DWG | 1 | 082623C-3300-DW-1572-0001 | 0 | B | IFA | INSTRUMENT MAIN CABLE ROUTING PYGAS | 2021-01-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 3300 | A8RX-TSC-3300-270-LST-001 | LST | 1 | 082623C-3300-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST STYRENE EXTRACTION (SE) UNIT | 2020-12-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3300 | A8RX-TSC-3300-653-FHA-001 | FHA | 1 | 082623C-3300-RT-1900-0201 | 0 | B | IFI | HAZID REPORT | 2020-10-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3300 | A8RX-TSC-3300-653-LAY-001 | LAY | 1 | 082623C-3300-DW-1933-0101 | 0 | B | IFA | FIRE FIGHTING LAYOUT (STYRENE) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3300 | A8RX-TSC-3300-653-LAY-002 | LAY | 2 | 082623C-3300-DW-1933-0201 | 0 | B | IFA | SAFETY AND PORTABLE FIRE EQUIPMENT LAYOUT (STYRENE) | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3300 | A8RX-TSC-3300-653-LAY-003 | LAY | 3 | 082623C-3300-DW-1950-0001 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT (STYRENE) | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3300 | A8RX-TSC-3300-653-LAY-004 | LAY | 4 | 082623C-3300-DW-1980-0001 | 0 | B | IFA | PASSIVE FIRE PROTECTION ZONE LAYOUT (STYRENE) | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3300 | A8RX-TSC-3300-653-LST-001 | LST | 1 | 082623C-3300-CN-1901-0003 | 0 | B | IFI | MSDS COLLECTION | 2021-01-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 3400 | A8RX-TSC-3400-210-DWG-001 | DWG | 1 | 082623C-3400-DW-1442-0001 | 0 | B | IFA | MAJOR UNDERGROUND PYE GAS | 2021-01-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-CAE-001 | CAE | 1 | 082623C-3400-NM-0013-0001 | 0 | B | IFA | CAUSE/EFFECT DIAGRAMS - UNIT 3400 | 2021-01-26 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-DBD-001 | DBD | 1 | 082623C-3400-CN-0007-0001 | 0 | B | IFA | PROCESS DESIGN BASIS - PYGAS HYDROGENATION UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-DBD-002 | DBD | 2 | 082623C-3400-NM-0001-0001 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - PYGAS HYDROGENATION UNIT (DESIGN CASE) | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-DBD-003 | DBD | 3 | 082623C-3400-NM-0001-0002 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - PYGAS HYDROGENATION UNIT (CHECK CASE 1) | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-DBD-004 | DBD | 4 | 082623C-3400-NM-0001-0003 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - PYGAS HYDROGENATION UNIT (CHECK CASE 2) | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-DST-001 | DST | 1 | 082623C-3400-SP-1500-0045 | 0 | B | IFI | DS FOR SAFETY MATL (PSV, TRV, BREATHER VALVES) - PYGAS HYDROGENATION UNIT | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-DST-002 | DST | 2 | 082623C-3400-SP-1500-0041 | 0 | B | IFI | DS FOR CRITICAL CONTROL VALVES - PYGAS HYDROGENATION UNIT | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-DST-003 | DST | 3 | 082623C-3400-SP-1500-0001 | 0 | B | IFI | DS FOR ANALYZERS - PYGAS HYDROGENATION UNIT | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-NAR-001 | NAR | 1 | 082623C-3400-CN-0009-0001 | 0 | B | IFA | PROCESS DESCRIPTION - PYGAS HYDROGENATION UNIT | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PFD-001 | PFD | 1 | 082623C-3400-PFD-0010-0001 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-10-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PFD-002 | PFD | 2 | 082623C-3400-PFD-0010-0002 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-10-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PFD-003 | PFD | 3 | 082623C-3400-PFD-0010-0003 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-10-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PFD-004 | PFD | 4 | 082623C-3400-PFD-0010-0004 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-10-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PFD-005 | PFD | 5 | 082623C-3400-PFD-0010-0005 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-10-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-001 | PID | 1 | 082623C-3400-PID-0021-0001 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-002 | PID | 2 | 082623C-3400-PID-0021-0002 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-003 | PID | 3 | 082623C-3400-PID-0021-0003 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-004 | PID | 4 | 082623C-3400-PID-0021-0004 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-005 | PID | 5 | 082623C-3400-PID-0021-0005 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-006 | PID | 6 | 082623C-3400-PID-0021-0006 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-007 | PID | 7 | 082623C-3400-PID-0021-0007 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-008 | PID | 8 | 082623C-3400-PID-0021-0008 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-009 | PID | 9 | 082623C-3400-PID-0021-0009 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-010 | PID | 10 | 082623C-3400-PID-0021-0010 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-011 | PID | 11 | 082623C-3400-PID-0021-0011 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-012 | PID | 12 | 082623C-3400-PID-0021-0012 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-013 | PID | 13 | 082623C-3400-PID-0021-0013 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-014 | PID | 14 | 082623C-3400-PID-0021-0014 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-015 | PID | 15 | 082623C-3400-PID-0021-0015 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-016 | PID | 16 | 082623C-3400-PID-0021-0016 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-017 | PID | 17 | 082623C-3400-PID-0021-0017 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-018 | PID | 18 | 082623C-3400-PID-0021-0018 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-019 | PID | 19 | 082623C-3400-PID-0021-0019 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-020 | PID | 20 | 082623C-3400-PID-0021-0020 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-021 | PID | 21 | 082623C-3400-PID-0021-0021 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-022 | PID | 22 | 082623C-3400-PID-0021-0022 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-023 | PID | 23 | 082623C-3400-PID-0021-0023 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-024 | PID | 24 | 082623C-3400-PID-0021-0024 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-025 | PID | 25 | 082623C-3400-PID-0021-0025 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-026 | PID | 26 | 082623C-3400-PID-0021-0026 | 0 | B | IFA | PROCESS PID - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-027 | PID | 27 | 082623C-3400-PID-0031-0001 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-028 | PID | 28 | 082623C-3400-PID-0031-0002 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-029 | PID | 29 | 082623C-3400-PID-0031-0003 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-030 | PID | 30 | 082623C-3400-PID-0031-0004 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-031 | PID | 31 | 082623C-3400-PID-0031-0005 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-032 | PID | 32 | 082623C-3400-PID-0031-0006 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-033 | PID | 33 | 082623C-3400-PID-0031-0007 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-034 | PID | 34 | 082623C-3400-PID-0031-0008 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-035 | PID | 35 | 082623C-3400-PID-0031-0009 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-PID-036 | PID | 36 | 082623C-3400-PID-0031-0010 | 0 | B | IFA | UTILITIES DIAGRAMS - PYGAS HYDROGENATION UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-SUM-001 | SUM | 1 | 082623C-3400-EL-0101 | 0 | B | IFA | PROCESS SIZED EQUIPMENT SUMMARY - PYGAS HYDROGENATION UNIT | 2020-12-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-SUM-002 | SUM | 2 | 082623C-3400-NM-0003-0001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - PYGAS HYDROGENATION UNIT | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-SUM-003 | SUM | 3 | 082623C-3400-NM-0004-0001 | 0 | B | IFA | CATALYST AND CHEMICALS CONSUMPTION SUMMARY - PYGAS HYDROGENATION UNIT | 2020-11-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-SUM-004 | SUM | 4 | 082623C-3400-NM-0005-0001 | 0 | B | IFA | EFFLUENT SUMMARY - PYGAS HYDROGENATION UNIT | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 3400 | A8RX-TSC-3400-225-SUM-005 | SUM | 5 | 082623C-3400-NM-0014-0001 | 0 | B | IFA | RELIEF LOAD SUMMARY - PYGAS HYDROGENATION UNIT | 2020-11-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 3400 | A8RX-TSC-3400-250-PLN-001 | PLN | 1 | 082623C-3400-DW-0051-0003 | 0 | B | IFA | UNIT PLOT-PLANS PYE GAS | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 3400 | A8RX-TSC-3400-250-PLN-002 | PLN | 2 | 082623C-3400-DW-0053-0003 | 0 | B | IFA | KEY PLOT-PLANS PYE GAS | 2020-11-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 3400 | A8RX-TSC-3400-265-HAC-001 | HAC | 1 | 082623C-3400-DW-1920-0001 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION PHG | 2021-01-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 3400 | A8RX-TSC-3400-265-LST-001 | LST | 1 | 082623C-3400-NM-1601-0001 | 0 | B | IFA | ELECTRICAL LOAD LIST - PYGAS | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 3400 | A8RX-TSC-3400-270-DWG-001 | DWG | 1 | 082623C-3400-DW-1572-0001 | 0 | B | IFA | INSTRUMENT MAIN CABLE ROUTING STIRENE EXTRACTION | 2021-01-26 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 3400 | A8RX-TSC-3400-270-LST-001 | LST | 1 | 082623C-3400-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST PYGAS HYDROGENATION (PGH) UNIT | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3400 | A8RX-TSC-3400-653-FHA-001 | FHA | 1 | 082623C-3400-RT-1900-0201 | 0 | B | IFI | HAZID REPORT | 2020-10-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3400 | A8RX-TSC-3400-653-LAY-001 | LAY | 1 | 082623C-3400-DW-1933-0101 | 0 | B | IFA | FIRE FIGHTING LAYOUT (PYGAS) | 2020-12-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3400 | A8RX-TSC-3400-653-LAY-002 | LAY | 2 | 082623C-3400-DW-1933-0201 | 0 | B | IFA | SAFETY AND PORTABLE FIRE EQUIPMENT LAYOUT (PYGAS) | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3400 | A8RX-TSC-3400-653-LAY-003 | LAY | 3 | 082623C-3400-DW-1950-0001 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT (PYGAS) | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3400 | A8RX-TSC-3400-653-LAY-004 | LAY | 4 | 082623C-3400-DW-1980-0001 | 0 | B | IFA | PASSIVE FIRE PROTECTION ZONE LAYOUT (PYGAS) | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 3400 | A8RX-TSC-3400-653-LST-001 | LST | 1 | 082623C-3400-CN-1901-0003 | 0 | B | IFI | MSDS COLLECTION | 2021-01-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4000 | A8RX-TSC-4000-225-PID-049 | PID | 49 | 082623C-4000-PID-1931-0001 | 0 | B | IFA | FIRE PROTECTION PIDS (NETWORK AND DISTRIBUTION) | 2020-12-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 4000 | A8RX-TSC-4000-250-PLN-001 | PLN | 1 | 082623C-4000-DW-0051-0003 | 0 | B | IFA | UNIT PLOT-PLANS INTERCONNECTING | 2020-11-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 4000 | A8RX-TSC-4000-250-PLN-002 | PLN | 2 | 082623C-4000-DW-0053-0003 | 0 | B | IFA | KEY PLOT-PLANS INTERCONNECTING | 2020-11-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-HEATERS & BOILERS | 4000 | A8RX-TSC-4000-255-SPC-001 | SPC | 1 | 082623C-4000-SP-0150-0001 | 0 | B | IFA | DATA SHEET FOR INDUSTRIAL STEAM BOILERS | 2020-11-26 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 4000 | A8RX-TSC-4000-255-SPC-500 | SPC | 500 | 082623C-4000-SP-0910-0001 | 0 | B | IFA | SP CENTRIFUGAL PUMPS (BFW) | 2020-12-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 4000 | A8RX-TSC-4000-255-SPC-501 | SPC | 501 | 082623C-4000-SP-1112-0001 | 0 | B | IFA | SPECIFICATION FOR SPECIAL PURPOSES STEAM TURBINE | 2020-12-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 4000 | A8RX-TSC-4000-255-SPC-502 | SPC | 502 | 082623C-4000-SP-1112-0002 | 0 | B | IFA | SPECIFICATION SPECIAL PURPOSES STEAM TURBINE | 2020-12-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 4000 | A8RX-TSC-4000-255-SPC-503 | SPC | 503 | 082623C-4000-SP-1112-0003 | 0 | B | IFA | SPEFICICATION FOR SPECIAL PURPOSES STEAM TURBINE | 2020-12-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 4000 | A8RX-TSC-4000-255-SPC-504 | SPC | 504 | 082623C-4000-SP-4121-0001 | 0 | B | IFA | SP STEAM TURBINE GENERATOR | 2020-12-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4000 | A8RX-TSC-4000-265-DWG-001 | DWG | 1 | 082623C-4000-DW-1622-0001 | 0 | B | IFA | ELECTRICAL MAIN CABLE ROUTING SGU | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4000 | A8RX-TSC-4000-265-HAC-001 | HAC | 1 | 082623C-4000-DW-1920-0001 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION ISBL UTILITIES | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DST-001 | DST | 1 | 4100-CA-D-11401 | 0 | B | IFA | BUILDINGS - SUMMARY TABLE | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-001 | DWG | 1 | 4100-CC-B-14000 | 0 | B | IFA | BUILDING - EO/EG ELECTRICAL SUBSTATION AND INSTRUMENT ROOM - PLANS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-002 | DWG | 2 | 4100-CC-B-14001 | 0 | B | IFA | BUILDING - EO/EG ELECTRICAL SUBSTATION AND INSTRUMENT ROOM - VIEWS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-003 | DWG | 3 | 4100-CC-B-14002 | 0 | B | IFA | BUILDING - EO/EG ELECTRICAL SUBSTATION AND INSTRUMENT ROOM - SECTIONS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-004 | DWG | 4 | 4100-CC-B-14005 | 0 | B | IFA | BUILDING - COOLING WATER ELECTRICAL SUBSTATION AND INSTRUMENT ROOM - PLANS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-005 | DWG | 5 | 4100-CC-B-14006 | 0 | B | IFA | BUILDING - COOLING WATER ELECTRICAL SUBSTATION AND INSTRUMENT ROOM - VIEWS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-006 | DWG | 6 | 4100-CC-B-14007 | 0 | B | IFA | BUILDING - COOLING WATER ELECTRICAL SUBSTATION AND INSTRUMENT ROOM - SECTIONS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-007 | DWG | 7 | 4100-CC-B-14010 | 0 | B | IFA | BUILDING - ETBE ELECTRICAL SUBSTATION AND INSTRUMENT ROOM - PLANS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-008 | DWG | 8 | 4100-CC-B-14011 | 0 | B | IFA | BUILDING - ETBE ELECTRICAL SUBSTATION AND INSTRUMENT ROOM - VIEWS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-009 | DWG | 9 | 4100-CC-B-14012 | 0 | B | IFA | BUILDING - ETBE ELECTRICAL SUBSTATION AND INSTRUMENT ROOM - SECTIONS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-010 | DWG | 10 | 4100-CC-B-14015 | 0 | B | IFA | BUILDING - CONTROL ROOM - PLANS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-011 | DWG | 11 | 4100-CC-B-14016 | 0 | B | IFA | BUILDING - CONTROL ROOM - VIEWS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 220 | ARCHITECTURAL | 4100 | A8RX-TSC-4100-220-DWG-012 | DWG | 12 | 4100-CC-B-14017 | 0 | B | IFA | BUILDING - CONTROL ROOM - SECTIONS | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-LAY-001 | LAY | 1 | 082623C-4100-DW-1625-0001 | 0 | B | IFA | SUBSTATION EQUIPMENT LAYOUT OPR-R71 - STEAM CRAKER | 2021-02-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-LAY-002 | LAY | 2 | 082623C-4100-DW-1625-0002 | 0 | B | IFA | SUBSTATION EQUIPMENT LAYOUT OPT-R-711 STEAM CRAKER | 2021-02-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-LAY-003 | LAY | 3 | 082623C-4100-DW-1625-0003 | 0 | B | IFA | SUBSTATION EQUIPMENT LAYOUT OPT-R-712 STEAM CRAKER | 2021-02-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-LAY-004 | LAY | 4 | 082623C-4100-DW-1625-0004 | 0 | B | IFA | SUBSTATION EQUIPMENT LAYOUT OPR-R82 - SE-PHG | 2021-02-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-LAY-005 | LAY | 5 | 082623C-4100-DW-1625-0005 | 0 | B | IFA | SUBSTATION EQUIPMENT LAYOUT OPR-R75-SGU | 2021-02-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-LAY-006 | LAY | 6 | 4100-EB-B-40031 | 0 | B | IFA | ELECTRICAL EQUIPMENT LAYOUT - EO/EG SUBSTATION | 2021-01-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-LAY-007 | LAY | 7 | 4100-EB-B-40032 | 0 | B | IFA | ELECTRICAL EQUIPMENT LAYOUT - COOLING WATER SUBSTATION | 2021-01-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-LAY-008 | LAY | 8 | 4100-EB-B-40033 | 0 | B | IFA | ELECTRICAL EQUIPMENT LAYOUT - ETBE SUBSTATION | 2021-02-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-SLD-001 | SLD | 1 | 082623C-4100-DW-1652-0001 | 0 | B | IFA | SUBSTATION SINGLE LINE DIAGRAM OPR-R71 - STEAM CRAKER | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-SLD-002 | SLD | 2 | 082623C-4100-DW-1652-0002 | 0 | B | IFA | SUBSTATION SINGLE LINE DIAGRAM OPT-R-711 STEAM CRAKER | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-SLD-003 | SLD | 3 | 082623C-4100-DW-1652-0003 | 0 | B | IFA | SUBSTATION SINGLE LINE DIAGRAM OPT-R-712 STEAM CRAKER | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-SLD-004 | SLD | 4 | 082623C-4100-DW-1652-0004 | 0 | B | IFA | SUBSTATION SINGLE LINE DIAGRAM OPR-R82 DE-PHG | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4100 | A8RX-TSC-4100-265-SLD-005 | SLD | 5 | 082623C-4100-DW-1652-0005 | 0 | B | IFA | SUBSTATION SINGLE LINE DIAGRAM OPR-R75 DGU | 2021-01-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4100 | A8RX-TSC-4100-270-DWG-001 | DWG | 1 | 082623C-4100-DW-1523-0001 | 0 | B | IFA | CONTROL AND TECHNICAL ROOM LAYOUT STEAM CRACKER - IAR-1 | 2021-02-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4100 | A8RX-TSC-4100-270-DWG-002 | DWG | 2 | 082623C-4100-DW-1523-0002 | 0 | B | IFA | CONTROL AND TECHNICAL ROOM LAYOUT STEAM CRACKER - IAR-2 | 2021-02-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4100 | A8RX-TSC-4100-270-DWG-003 | DWG | 3 | 082623C-4100-DW-1523-0003 | 0 | B | IFA | CONTROL AND TECHNICAL ROOM LAYOUT PERIPHERAL UNITS - IAR-3 | 2021-02-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4100 | A8RX-TSC-4100-270-LAY-001 | LAY | 1 | 4100-HB-B-55011 | 0 | B | IFA | CONTROL ROOM EQUIPMENT LAYOUT | 2021-01-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4100 | A8RX-TSC-4100-270-LAY-002 | LAY | 2 | 4100-HB-C-55012 | 0 | B | IFA | EQUIPMENT LAYOUT - EO/EG INSTRUMENT ROOM | 2021-01-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4100 | A8RX-TSC-4100-270-LAY-003 | LAY | 3 | 4100-HB-C-55013 | 0 | B | IFA | EQUIPMENT LAYOUT - COOLING WATER INSTRUMENT ROOM | 2021-01-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4100 | A8RX-TSC-4100-270-LAY-004 | LAY | 4 | 4100-HB-C-55014 | 0 | B | IFA | EQUIPMENT LAYOUT - ETBE INSTRUMENT ROOM | 2021-01-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 4180 | A8RX-TSC-4180-210-LAY-001 | LAY | 1 | 4180-CG-B-12010 | 0 | B | IFA | ETBE AREA - ROADS AND PAVING - PLAN AND SECTIONS | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 4180 | A8RX-TSC-4180-210-LAY-002 | LAY | 2 | 4180-CG-B-12011 | 0 | B | IFA | EO/MEG/DEG/TEG AREA - ROADS AND PAVING - PLAN AND SECTIONS | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 4180 | A8RX-TSC-4180-210-LAY-003 | LAY | 3 | 4180-CG-B-12012 | 0 | B | IFA | COOLING TOWER AREA - ROADS AND PAVING - PLAN AND SECTIONS | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 4200 | A8RX-TSC-4200-200-SUM-001 | SUM | 1 | 082623C-4200-EL-0101 | 0 | B | IFA | PROCESS SIZED EQUIPMENT SUMMARY - CONDENSATE TREATMENT | 2020-11-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 4200 | A8RX-TSC-4200-210-DWG-001 | DWG | 1 | 082623C-4200-DW-1442-0001 | 0 | B | IFA | MAJOR UNDERGROUND CONDENSATE | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-CAE-001 | CAE | 1 | 082623C-4200-NM-0013-0001 | 0 | B | IFA | CAUSE AND EFFECT DIAGRAMS - CONDENSATE TREATMENT UNIT | 2021-01-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-DBD-001 | DBD | 1 | 082623C-4200-CN-0007-0001 | 0 | B | IFA | PROCESS DESIGN BASIS - CONDENSATE TREATMENT UNIT | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-DBD-002 | DBD | 2 | 082623C-4200-NM-0001-0001 | 0 | B | IFA | HEAT AND MATERIAL BALANCE - CONDENSATE TREATMENT UNIT | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-DST-001 | DST | 1 | 082623C-4200-SP-1500-0065 | 0 | B | IFI | DS FOR ANALYZERS | 2021-01-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-LST-001 | LST | 1 | 082623C-4200-NM-0005-0001 | 0 | B | IFA | EFFLUENT LIST - CONDENSATE TREATMENT UNIT | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-NAR-002 | NAR | 2 | 082623C-4200-CN-0009-0001 | 0 | B | IFA | PROCESS DESCRIPTION - CONDENSATE TREATMENT UNIT | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-PFD-001 | PFD | 1 | 082623C-4200-PFD-0010-0001 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-PFD-002 | PFD | 2 | 082623C-4200-PFD-0010-0002 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-PFD-003 | PFD | 3 | 082623C-4200-PFD-0010-0003 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-PFD-004 | PFD | 4 | 082623C-4200-PFD-0010-0004 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-PFD-005 | PFD | 5 | 082623C-4200-PFD-0010-0005 | 0 | B | IFA | BLOCK FLOW DIAGRAM - CONDENSATE TREATMENT UNIT | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-SUM-001 | SUM | 1 | 082623C-4200-NM-0003-0001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - CONDENSATE TREATMENT UNIT | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4200 | A8RX-TSC-4200-225-SUM-002 | SUM | 2 | 082623C-4200-NM-0004-0001 | 0 | B | IFA | CHEMICAL CONSUMPTION SUMMARY - CONDENSATE TREATMENT UNIT | 2020-12-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4200 | A8RX-TSC-4200-270-LST-001 | LST | 1 | 082623C-4200-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST CONDENSATE TREATMENT | 2020-12-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4300 | A8RX-TSC-4300-270-LST-001 | LST | 1 | 082623C-4300-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST ISBL UTILITIES | 2020-12-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-CAE-001 | CAE | 1 | 082623C-4310-NM-0013-0001 | 0 | B | IFA | CAUSE AND EFFECT DIAGRAMS - FUEL GAS | 2021-01-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-DBD-001 | DBD | 1 | 082623C-4310-NM-0001-0001 | 0 | B | IFA | HEAT AND MATERIAL BALANCE - FUEL GAS | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-DBD-002 | DBD | 2 | 082623C-4310-CN-0007-0001 | 0 | B | IFA | PROCESS DESIGN BASIS - FULE GAS | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-DST-001 | DST | 1 | 082623C-4310-SP-1500-0045 | 0 | B | IFI | DS FOR SAFETY MATL (PSV, TRV, BREATHER VALVES) | 2021-01-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-DST-002 | DST | 2 | 082623C-4310-SP-1500-0065 | 0 | B | IFI | DS FOR ANALYZERS | 2021-01-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-NAR-002 | NAR | 2 | 082623C-4310-CN-0009-0001 | 0 | B | IFA | PROCESS DESCRIPTION - FUEL GAS | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-PFD-001 | PFD | 1 | 082623C-4310-PFD-0010-0001 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-PFD-002 | PFD | 2 | 082623C-4310-PFD-0010-0002 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-PFD-003 | PFD | 3 | 082623C-4310-PFD-0010-0003 | 0 | B | IFA | BLOCK FLOW DIAGRAM - FUEL GAS | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4310 | A8RX-TSC-4310-225-SUM-001 | SUM | 1 | 082623C-4310-NM-0003-0001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - FUEL GAS | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4320 | A8RX-TSC-4320-225-CAE-001 | CAE | 1 | 082623C-4320-NM-0013-0001 | 0 | B | IFA | CAUSE AND EFFECT DIAGRAMS - SEWER SYSTEM | 2021-01-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4320 | A8RX-TSC-4320-225-DBD-001 | DBD | 1 | 082623C-4320-NM-0001-0001 | 0 | B | IFA | HEAT AND MATERIAL BALANCE - SEWER SYSTEM | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4320 | A8RX-TSC-4320-225-DBD-002 | DBD | 2 | 082623C-4320-CN-0007-0001 | 0 | B | IFA | PROCESS DESIGN BASIS - SEWER SYSTEM | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4320 | A8RX-TSC-4320-225-NAR-002 | NAR | 2 | 082623C-4320-CN-0009-0001 | 0 | B | IFA | PROCESS DESCRIPTION - SEWER SYSTEM | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4320 | A8RX-TSC-4320-225-PFD-001 | PFD | 1 | 082623C-4320-PFD-0010-0001 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4320 | A8RX-TSC-4320-225-PFD-002 | PFD | 2 | 082623C-4320-PFD-0010-0002 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4320 | A8RX-TSC-4320-225-PFD-003 | PFD | 3 | 082623C-4320-PFD-0010-0003 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4320 | A8RX-TSC-4320-225-PFD-004 | PFD | 4 | 082623C-4320-PFD-0010-0004 | 0 | B | IFA | BLOCK FLOW DIAGRAM - SEWER SYSTEM | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4320 | A8RX-TSC-4320-225-SUM-001 | SUM | 1 | 082623C-4320-NM-0003-0001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - SEWER SYSTEM | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 4400 | A8RX-TSC-4400-200-SUM-001 | SUM | 1 | 082623C-4400-EL-0101 | 0 | B | IFA | PROCESS SIZED EQUIPMENT SUMMARY - INTERCONNECTING | 2020-11-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-DBD-001 | DBD | 1 | 082623C-4400-NM-0001-0001 | 0 | B | IFA | HEAT AND MATERIAL BALANCE - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-001 | PID | 1 | 082623C-4400-PID-0090-0001 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-002 | PID | 2 | 082623C-4400-PID-0090-0002 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-003 | PID | 3 | 082623C-4400-PID-0090-0003 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-004 | PID | 4 | 082623C-4400-PID-0090-0004 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-005 | PID | 5 | 082623C-4400-PID-0090-0005 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-006 | PID | 6 | 082623C-4400-PID-0090-0006 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-007 | PID | 7 | 082623C-4400-PID-0090-0007 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-008 | PID | 8 | 082623C-4400-PID-0090-0008 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-009 | PID | 9 | 082623C-4400-PID-0090-0009 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-010 | PID | 10 | 082623C-4400-PID-0090-0010 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-011 | PID | 11 | 082623C-4400-PID-0090-0011 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-012 | PID | 12 | 082623C-4400-PID-0090-0012 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-013 | PID | 13 | 082623C-4400-PID-0090-0013 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-014 | PID | 14 | 082623C-4400-PID-0090-0014 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-015 | PID | 15 | 082623C-4400-PID-0090-0015 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-016 | PID | 16 | 082623C-4400-PID-0090-0016 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-017 | PID | 17 | 082623C-4400-PID-0090-0017 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-018 | PID | 18 | 082623C-4400-PID-0090-0018 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-019 | PID | 19 | 082623C-4400-PID-0090-0019 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-020 | PID | 20 | 082623C-4400-PID-0090-0020 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-021 | PID | 21 | 082623C-4400-PID-0031-0021 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-022 | PID | 22 | 082623C-4400-PID-0031-0022 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-023 | PID | 23 | 082623C-4400-PID-0031-0023 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-024 | PID | 24 | 082623C-4400-PID-0031-0024 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-025 | PID | 25 | 082623C-4400-PID-0031-0025 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-026 | PID | 26 | 082623C-4400-PID-0031-0026 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-027 | PID | 27 | 082623C-4400-PID-0031-0027 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-028 | PID | 28 | 082623C-4400-PID-0031-0028 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-029 | PID | 29 | 082623C-4400-PID-0031-0029 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-030 | PID | 30 | 082623C-4400-PID-0031-0030 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-031 | PID | 31 | 082623C-4400-PID-0031-0031 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-032 | PID | 32 | 082623C-4400-PID-0031-0032 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-033 | PID | 33 | 082623C-4400-PID-0031-0033 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-034 | PID | 34 | 082623C-4400-PID-0031-0034 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-035 | PID | 35 | 082623C-4400-PID-0031-0035 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-036 | PID | 36 | 082623C-4400-PID-0031-0036 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-037 | PID | 37 | 082623C-4400-PID-0031-0037 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-038 | PID | 38 | 082623C-4400-PID-0031-0038 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-039 | PID | 39 | 082623C-4400-PID-0031-0039 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-040 | PID | 40 | 082623C-4400-PID-0031-0040 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-041 | PID | 41 | 082623C-4400-PID-0031-0041 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-042 | PID | 42 | 082623C-4400-PID-0031-0042 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-043 | PID | 43 | 082623C-4400-PID-0031-0043 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-044 | PID | 44 | 082623C-4400-PID-0031-0044 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-045 | PID | 45 | 082623C-4400-PID-0031-0045 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-046 | PID | 46 | 082623C-4400-PID-0031-0046 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-047 | PID | 47 | 082623C-4400-PID-0031-0047 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-048 | PID | 48 | 082623C-4400-PID-0031-0048 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-049 | PID | 49 | 082623C-4400-PID-0031-0049 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-050 | PID | 50 | 082623C-4400-PID-0031-0050 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-051 | PID | 51 | 082623C-4400-PID-0031-0051 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-052 | PID | 52 | 082623C-4400-PID-0031-0052 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-053 | PID | 53 | 082623C-4400-PID-0031-0053 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-054 | PID | 54 | 082623C-4400-PID-0031-0054 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-055 | PID | 55 | 082623C-4400-PID-0031-0055 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-056 | PID | 56 | 082623C-4400-PID-0031-0056 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-057 | PID | 57 | 082623C-4400-PID-0031-0057 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-058 | PID | 58 | 082623C-4400-PID-0031-0058 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-059 | PID | 59 | 082623C-4400-PID-0031-0059 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-060 | PID | 60 | 082623C-4400-PID-0031-0060 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-061 | PID | 61 | 082623C-4400-PID-0031-0061 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-062 | PID | 62 | 082623C-4400-PID-0031-0062 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-063 | PID | 63 | 082623C-4400-PID-0031-0063 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-064 | PID | 64 | 082623C-4400-PID-0031-0064 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-065 | PID | 65 | 082623C-4400-PID-0031-0065 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-066 | PID | 66 | 082623C-4400-PID-0031-0066 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-067 | PID | 67 | 082623C-4400-PID-0031-0067 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-PID-068 | PID | 68 | 082623C-4400-PID-0031-0068 | 0 | B | IFA | PROCESS PID - INTERCONNECTING | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4400 | A8RX-TSC-4400-225-SUM-001 | SUM | 1 | 082623C-4400-NM-0003-0001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - INTERCONNECTING | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4400 | A8RX-TSC-4400-265-LST-001 | LST | 1 | 082623C-4400-NM-1601-0001 | 0 | B | IFA | ELECTRICAL LOAD LIST - INTERCONNECTING | 2020-12-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4400 | A8RX-TSC-4400-270-LST-001 | LST | 1 | 082623C-4400-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST ISBL INTERCONNECTION | 2020-12-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4400 | A8RX-TSC-4400-653-LAY-001 | LAY | 1 | 082623C-4400-DW-1950-0001 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT (INTERCONNECTING) | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4400 | A8RX-TSC-4400-653-LAY-002 | LAY | 2 | 082623C-4400-DW-1980-0001 | 0 | B | IFA | PASSIVE FIRE PROTECTION ZONE LAYOUT (INTERCONNECTING) | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4400 | A8RX-TSC-4400-653-LAY-003 | LAY | 3 | 082623C-4400-DW-1933-0101 | 0 | B | IFA | FIRE FIGHTING LAYOUT (INTERCONNECTING) | 2020-12-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-CAE-001 | CAE | 1 | 4500-ZA-D-71103 | 0 | B | IFA | CAUSE AND EFFECT DIAGRAMS - COOLING WATER | 2020-12-21 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-DBD-001 | DBD | 1 | 4500-ZA-E-70001 | 0 | B | IFA | UTILITIES DESIGN BASIS - COOLING TOWER SYSTEM | 2020-10-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-MSD-001 | MSD | 1 | 4500-GD-B-75300 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM COOLING WATER N°1 | 2021-02-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-MSD-002 | MSD | 2 | 4500-GD-B-75301 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM COOLING WATER N°2 | 2021-02-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-MSD-003 | MSD | 3 | 4500-GD-B-75302 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM COOLING WATER N°3 | 2021-02-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-NAR-001 | NAR | 1 | 4500-ZA-E-70003 | 0 | B | IFA | ISBL UTILITY SYSTEM DESCRIPTION - COOLING WATER SYSTEM | 2021-02-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-PFD-001 | PFD | 1 | 4500-GD-B-75100 | 0 | B | IFA | ISBL UTILITY FLOW DIAGRAM (COOLING SYSTEM) N° 1 | 2020-10-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-PFD-002 | PFD | 2 | 4500-GD-B-75101 | 0 | B | IFA | ISBL UTILITY FLOW DIAGRAM (COOLING SYSTEM) N° 2 | 2020-10-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-PFD-003 | PFD | 3 | 4500-GD-B-75102 | 0 | B | IFA | ISBL UTILITY FLOW DIAGRAM (COOLING SYSTEM) N° 3 | 2020-10-12 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-PID-001 | PID | 1 | 4500-GD-B-76500 | 0 | B | IFA | PROCESS PID COOLING WATER SYSTEM N° 1 | 2020-11-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-PID-002 | PID | 2 | 4500-GD-B-76501 | 0 | B | IFA | PROCESS PID COOLING WATER SYSTEM N° 2 | 2020-11-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-PID-003 | PID | 3 | 4500-GD-B-76502 | 0 | B | IFA | PROCESS PID COOLING WATER SYSTEM N° 3 | 2020-11-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-PID-004 | PID | 4 | 4500-GD-B-76503 | 0 | B | IFA | PROCESS PID COOLING WATER SYSTEM N° 4 | 2020-11-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-PID-005 | PID | 5 | 4500-GD-B-76504 | 0 | B | IFA | PROCESS PID COOLING WATER SYSTEM N° 5 | 2020-11-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-PID-006 | PID | 6 | 4500-GD-B-76505 | 0 | B | IFA | PROCESS PID COOLING WATER SYSTEM N° 6 | 2020-11-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-RPT-001 | RPT | 1 | 4500-ZA-E-70008 | 0 | B | IFA | HEAT AND MATERIAL BALANCES -- COOLING WATER | 2020-12-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-RPT-002 | RPT | 2 | 4500-ZA-D-70019 | 0 | B | IFA | MATERIAL SELECTION REPORT - COOLING WATER SYSTEM | 2021-01-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-SUM-001 | SUM | 1 | 4500-ZA-E-70026 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - COOLING WATER | 2021-02-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-SUM-002 | SUM | 2 | 4500-ZA-E-70029 | 0 | B | IFA | EFFLUENT SUMMARY - COOLING WATER | 2020-12-31 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-SUM-003 | SUM | 3 | 4500-ZA-E-70032 | 0 | B | IFA | PROCESS SIZED EQUIPMENT SUMMARY - COOLING WATER | 2020-11-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4500 | A8RX-TSC-4500-225-SUM-004 | SUM | 4 | 4500-ZA-E-70016 | 0 | B | IFA | CATALYST AND CHEMICAL SUMMARY COOLING WATER UNIT | 2020-12-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 4500 | A8RX-TSC-4500-250-LAY-101 | LAY | 101 | 4500-GB-B-65130 | 0 | B | IFA | COOLING TOWER AREA - UNIT PLOT PLAN | 2020-11-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 4500 | A8RX-TSC-4500-255-SUM-501 | SUM | 501 | 4500-MA-E-30014 | 0 | B | IFA | EQUIPMENT SUMMARY FOR UNIT 4500 | 2020-11-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4500 | A8RX-TSC-4500-265-LAY-001 | LAY | 1 | 4500-EB-A-40043 | 0 | B | IFA | ELECTRICAL AND INSTRUMENT COOLING WATER UNIT CABLE ROUTING | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4500 | A8RX-TSC-4500-265-SLD-001 | SLD | 1 | 4500-EC-B-40013 | 0 | B | IFA | KEY SINGLE LINE DIAGRAM COOLING WATER UNIT SUBSTATION | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4500 | A8RX-TSC-4500-270-DTA-002 | DTA | 2 | 4500-SA-E-50012 | 0 | B | IFA | INSTRUMENT INDEX FOR COOLING WATER - UNIT 4500 | 2020-12-24 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4500 | A8RX-TSC-4500-653-HAC-001 | HAC | 1 | 4500-ZB-B-85013 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION LAYOUT - COOLING TOWER AREA | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4500 | A8RX-TSC-4500-653-LAY-001 | LAY | 1 | 4500-ZB-B-85007 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT - COOLING TOWER AREA | 2021-01-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4500 | A8RX-TSC-4500-653-LAY-002 | LAY | 2 | 4500-ZB-B-85010 | 0 | B | IFA | FIREPROOFING ZONE LAYOUT - COOLING TOWER AREA | 2021-01-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4500 | A8RX-TSC-4500-653-LAY-003 | LAY | 3 | 4500-ZB-A-85022 | 0 | B | IFA | FIREWATER DISTRIBUTION LAYOUT - COOLING TOWER AREA | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 200 | ENGNEERING | 4600 | A8RX-TSC-4600-200-SUM-001 | SUM | 1 | 082623C-4600-EL-0101 | 0 | B | IFA | PROCESS SIZED EQUIPMENT SUMMARY - STEAM GENERATION | 2020-11-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 210 | CIVIL | 4600 | A8RX-TSC-4600-210-DWG-001 | DWG | 1 | 082623C-4600-DW-1442-0001 | 0 | B | IFA | MAJOR UNDERGROUND STEAM GENERATION | 2021-01-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4600 | A8RX-TSC-4600-225-PFD-001 | PFD | 1 | 082623C-4600-PFD-0010-0001 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4600 | A8RX-TSC-4600-225-PFD-002 | PFD | 2 | 082623C-4600-PFD-0010-0002 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4600 | A8RX-TSC-4600-225-PFD-003 | PFD | 3 | 082623C-4600-PFD-0010-0003 | 0 | B | IFA | PROCESS FLOW DIAGRAMS - ISBL UTILITIES | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4600 | A8RX-TSC-4600-265-HAC-001 | HAC | 1 | 082623C-4600-DW-1920-0001 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION SGU | 2021-01-07 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4600 | A8RX-TSC-4600-265-LST-001 | LST | 1 | 082623C-4600-NM-1601-0001 | 0 | B | IFA | ELECTRICAL LOAD LIST - STEAM GENERATION | 2020-12-21 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4600 | A8RX-TSC-4600-270-LST-001 | LST | 1 | 082623C-4600-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST STEAM GENERATION UNIT | 2020-12-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4600 | A8RX-TSC-4600-653-LAY-001 | LAY | 1 | 082623C-4600-DW-1933-0101 | 0 | B | IFA | FIRE FIGHTING LAYOUT (STEAM GENERATION) | 2021-01-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4600 | A8RX-TSC-4600-653-LAY-002 | LAY | 2 | 082623C-4600-DW-1933-0201 | 0 | B | IFA | SAFETY AND PORTABLE FIRE EQUIPMENT LAYOUT (STEAM GENERATION) | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4600 | A8RX-TSC-4600-653-LAY-003 | LAY | 3 | 082623C-4600-DW-1950-0001 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT (STEAM GENERATION) | 2021-01-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 4600 | A8RX-TSC-4600-653-LAY-004 | LAY | 4 | 082623C-4600-DW-1980-0001 | 0 | B | IFA | PASSIVE FIRE PROTECTION ZONE LAYOUT (STEAM GENERATION) | 2021-01-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-CAE-001 | CAE | 1 | 082623C-4610-NM-0013-0001 | 0 | B | IFA | CAUSE AND EFFECT DIAGRAMS - BOILER FEED WATER | 2021-01-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-DBD-001 | DBD | 1 | 082623C-4610-CN-0007-0001 | 0 | B | IFA | PROCESS DESIGN BASIS - BOILER FEED WATER | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-DBD-002 | DBD | 2 | 082623C-4610-NM-0001-0001 | 0 | B | IFA | HEAT AND MATERIAL BALANCE - BOILER FEED WATER | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-DST-001 | DST | 1 | 082623C-4610-SP-1500-0041 | 0 | B | IFI | DS FOR CONTROL VALVES | 2021-01-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-DST-002 | DST | 2 | 082623C-4610-SP-1500-0045 | 0 | B | IFI | DS FOR SAFETY MATL (PSV, TRV, BREATHER VALVES) | 2021-01-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-DST-003 | DST | 3 | 082623C-4610-SP-1500-0065 | 0 | B | IFI | DS FOR ANALYZERS | 2021-01-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-LST-001 | LST | 1 | 082623C-4610-NM-0005-0001 | 0 | B | IFA | EFFLUENT LIST - BOILER FEED WATER | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-NAR-002 | NAR | 2 | 082623C-4610-CN-0009-0001 | 0 | B | IFA | PROCESS DESCRIPTION - BOILER FEED WATER | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-SUM-001 | SUM | 1 | 082623C-4610-NM-0003-0001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - BOILER FEED WATER | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4610 | A8RX-TSC-4610-225-SUM-002 | SUM | 2 | 082623C-4610-NM-0004-0001 | 0 | B | IFA | CHEMICAL CONSUMPTION SUMMARY - BOILER FEED WATER | 2020-12-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-CAE-001 | CAE | 1 | 082623C-4620-NM-0013-0001 | 0 | B | IFA | CAUSE AND EFFECT DIAGRAMS - STEAM AND POWER GENERATION | 2021-01-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-DBD-001 | DBD | 1 | 082623C-4620-CN-0007-0001 | 0 | B | IFA | PROCESS DESIGN BASIS - STEAM AND POWER GENERATION | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-DBD-002 | DBD | 2 | 082623C-4620-NM-0001-0002 | 0 | B | IFA | HEAT AND MATERIAL BALANCE - STEAM AND POWER GENERATION | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-DST-001 | DST | 1 | 082623C-4620-SP-1500-0042 | 0 | B | IFI | DS FOR CONTROL VALVES | 2021-01-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-DST-002 | DST | 2 | 082623C-4620-SP-1500-0046 | 0 | B | IFI | DS FOR SAFETY MATL (PSV, TRV, BREATHER VALVES) | 2021-01-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-DST-003 | DST | 3 | 082623C-4620-SP-1500-0065 | 0 | B | IFI | DS FOR ANALYZERS | 2021-01-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-LST-001 | LST | 1 | 082623C-4620-NM-0005-0001 | 0 | B | IFA | EFFLUENT LIST - STEAM AND POWER GENERATION | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-NAR-002 | NAR | 2 | 082623C-4620-CN-0009-0001 | 0 | B | IFA | PROCESS DESCRIPTION - STEAM AND POWER GENERATION | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-PFD-001 | PFD | 1 | 082623C-4620-PFD-0010-0001 | 0 | B | IFA | BLOCK FLOW DIAGRAM - STEAM AND POWER GENERATION | 2020-10-30 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-PHL-001 | PHL | 1 | 082623C-4620-CN-0008-0001 | 0 | B | IFA | CONTROL PHILOSOPHY (CTRL AND FUCTIONAL DESCN) | 2020-11-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-SUM-001 | SUM | 1 | 082623C-4620-NM-0003-0001 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - STEAM AND POWER GENERATION | 2021-01-06 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 4620 | A8RX-TSC-4620-225-SUM-002 | SUM | 2 | 082623C-4620-NM-0004-0001 | 0 | B | IFA | CHEMICAL CONSUMPTION SUMMARY - STEAM AND POWER GENERATION | 2020-12-05 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-DBD-001 | DBD | 1 | 4700-EA-E-40001 | 0 | B | IFA | ELECTRICAL DESIGN BASIS | 2020-10-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-DTA-001 | DTA | 1 | 4700-EE-D-40021 | 0 | B | IFA | ELECTRICAL LOAD LIST | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-DTA-002 | DTA | 2 | 4700-EE-D-40022 | 0 | B | IFA | ELECTRICAL SIZED EQUIPMENT LIST | 2021-01-11 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-LST-001 | LST | 1 | 082623C-4700-NM-1601-0001 | 0 | B | IFA | ELECTRICAL LOAD LIST - POWER DISTRIBUTION SYSTEM | 2020-12-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-SLD-001 | SLD | 1 | 4700-EC-B-40011 | 0 | B | IFA | OVERALL KEY SINGLE LINE DIAGRAM | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-SPC-001 | SPC | 1 | 4700-EA-E-40051 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR MV SWITCHGEAR AND MCC | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-SPC-002 | SPC | 2 | 4700-EA-E-40052 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR LV SWITCHGEAR AND MCC | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-SPC-003 | SPC | 3 | 4700-EA-E-40053 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR MV/LV TRANSFORMERS | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-SPC-004 | SPC | 4 | 4700-EA-E-40054 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR MV MOTORS | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 4700 | A8RX-TSC-4700-265-SPC-005 | SPC | 5 | 4700-EA-E-40055 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR UPS SYSTEMS | 2021-01-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4800 | A8RX-TSC-4800-270-DIA-001 | DIA | 1 | 4800-HD-C-56001 | 0 | B | IFA | OVERALL INTEGRATED CONTROL SYSTEMS ARCHITECTURE BLOCK DIAGRAM | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4800 | A8RX-TSC-4800-270-PHL-001 | PHL | 1 | 4800-HA-E-51001 | 0 | B | IFA | CONTROL SYSTEMS PHILOSOPHY | 2020-10-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4800 | A8RX-TSC-4800-270-SPC-001 | SPC | 1 | 4800-HA-E-51021 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR DCS | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4800 | A8RX-TSC-4800-270-SPC-002 | SPC | 2 | 4800-HA-E-51022 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR ESD | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4800 | A8RX-TSC-4800-270-SPC-003 | SPC | 3 | 4800-HA-E-51023 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR MMS | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4800 | A8RX-TSC-4800-270-SPC-004 | SPC | 4 | 4800-HA-E-51024 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR FIRE AND GAS SYSTEM | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4800 | A8RX-TSC-4800-270-SPC-005 | SPC | 5 | 4800-HA-E-51025 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR BMS | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4800 | A8RX-TSC-4800-270-SPC-006 | SPC | 6 | 4800-HA-E-51026 | 0 | B | IFA | TECHNICAL SPECIFICATION FOR FLUGAS MONITORING SYSTEM | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4800 | A8RX-TSC-4800-270-SPC-007 | SPC | 7 | 4800-HA-E-51002 | 0 | B | IFA | INSTRUMENTS AND CONTROL SYSTEMS SPECIFICATION FOR PACKAGED EQUIPMENT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 275 | TELECOM | 4800 | A8RX-TSC-4800-275-DIA-001 | DIA | 1 | 4800-HD-C-57001 | 0 | B | IFA | OVERALL TELECOM SYSTEM ARCHITECTURE BLOCK DIAGRAM | 2020-12-01 |  |  |  |  | PLH
A8RX-TEC/SAI | 275 | TELECOM | 4800 | A8RX-TSC-4800-275-PHL-001 | PHL | 1 | 4800-HA-E-52001 | 0 | B | IFA | TELECOM SYSTEMS PHILOSOPHY | 2020-10-20 |  |  |  |  | PLH
A8RX-TEC/SAI | 240 | UNDEGROUND | 4900 | A8RX-TSC-4900-240-LAY-001 | LAY | 1 | 4900-CF-B-66100 | 0 | B | IFA | ETBE AREA - UNDERGROUND BASIC LAYOUT | 2020-12-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 240 | UNDEGROUND | 4900 | A8RX-TSC-4900-240-LAY-002 | LAY | 2 | 4900-CF-B-66101 | 0 | B | IFA | EO/MEG/DEG/TEG AREA - UNDERGROUND BASIC LAYOUT | 2020-11-19 |  |  |  |  | PLH
A8RX-TEC/SAI | 240 | UNDEGROUND | 4900 | A8RX-TSC-4900-240-LAY-003 | LAY | 3 | 4900-CF-B-66102 | 0 | B | IFA | COOLING TOWER AREA - UNDERGROUND BASIC LAYOUT | 2020-12-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 4900 | A8RX-TSC-4900-270-LST-001 | LST | 1 | 082623C-4900-NM-1551-0001 | 0 | B | IFA | INSTRUMENT LIST UG PIPING INCLUDING FIRE WATER NETWORKS | 2020-12-28 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 7110 | A8RX-TSC-7110-500-CWP-001 | CWP | 1 | 7110-ZA-E-02000 | 0 | B | IFA | CONSTRUCTION TEMPORARY FACILITIES - DETAIL PLOT PLAN OF ISBL TEMPORARY FACILITY INCLUDING PKN ORLEN/PMC FACILITY | 2021-02-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 7110 | A8RX-TSC-7110-500-CWP-002 | CWP | 2 | 7110-ZA-E-02001 | 0 | B | IFI | TEMPORARY UTILITIES REQUIREMENTS (ELECTRIC POWER, POTABLE WATER, SEWAGE) | 2021-02-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 7110 | A8RX-TSC-7110-500-CWP-003 | CWP | 3 | 7110-ZA-E-02002 | 0 | B | IFA | TEMPORARY FACILITIES - DETAIL PLOT PLAN OF ISBL TEMPORARY LAYDOWN, STORAGE AREA | 2021-02-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 500 | CONSTRUCTION | 7110 | A8RX-TSC-7110-500-CWP-004 | CWP | 4 | 7110-ZA-E-02003 | 0 | B | IFA | TEMPORARY FACILTIES - DETAIL PLOT PLAN OF ISBL TEMPORARY PARKING AS WELL AS PARKING PEAKS FOR LABOR TRANSPORT AND TRUCK DELIVERIES. | 2021-02-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 215 | STRUCTURAL | 8000 | A8RX-TSC-8000-215-PLN-001 | PLN | 1 | 8000-CD-B-16020 | 0 | B | IFA | PIPE RACK - STEEL STRUCTURES - PLANS AND ELEVATIONS | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 215 | STRUCTURAL | 8000 | A8RX-TSC-8000-215-PLN-002 | PLN | 2 | 8000-CD-B-16030 | 0 | B | IFA | EQUIPMENT STRUCTURE - STEEL STRUCTURES - PLANS AND ELEVATIONS | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 215 | STRUCTURAL | 8000 | A8RX-TSC-8000-215-PLN-003 | PLN | 3 | 8000-CD-B-16040 | 0 | B | IFA | SHELTER - STEEL STRUCTURES - PLANS AND ELEVATIONS | 2020-12-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-CAE-001 | CAE | 1 | 8000-ZA-E-71104 | 0 | B | IFA | CAUSE AND EFFECT DIAGRAMS - EO/EG UNIT | 2020-12-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-DBD-001 | DBD | 1 | 8000-ZA-E-70000 | 0 | B | IFA | PROCESS DESIGN BASIS - EO/EG UNIT | 2020-10-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-DST-001 | DST | 1 | 8000-ZA-D-71000 | 0 | B | IFA | DATA SHEET FOR CRITICAL CONTROL VALVE EO/EG UNIT | 2021-02-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-DST-002 | DST | 2 | 8000-ZA-D-71001 | 0 | B | IFA | DATA SHEET FOR PSV EO/EG UNIT | 2021-02-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-DST-003 | DST | 3 | 8000-ZA-D-71005 | 0 | B | IFA | DATA SHEET FOR ANALYZER EO/EG UNIT | 2021-02-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-NAR-001 | NAR | 1 | 8000-ZA-E-70002 | 0 | B | IFA | PROCESS DESCRIPTION - EO/EG UNIT | 2021-02-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-NAR-002 | NAR | 2 | 8000-ZA-E-71105 | 0 | B | IFA | CONTROL NARRATIVES FOR COMPLEX LOOPS - EO/EG | 2021-02-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-PRC-001 | PRC | 1 | 8000-ZA-E-70020 | 0 | B | IFA | HIGH LEVEL DESCRIPTION OF MAIN OPERATING ISSUES FOR EO/EG | 2021-02-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-RPT-001 | RPT | 1 | 8000-ZA-E-70006 | 0 | B | IFA | HEAT AND MATERIAL BALANCES - EO/EG UNIT | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-SUM-001 | SUM | 1 | 8000-ZA-E-70014 | 0 | B | IFA | CATALYST AND CHEMICAL SUMMARY EO/EG UNIT | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-SUM-002 | SUM | 2 | 8000-ZA-E-70024 | 0 | B | IFA | UTILITY CONSUMPTION SUMMARY - EO/EG | 2021-02-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-SUM-003 | SUM | 3 | 8000-ZA-E-70027 | 0 | B | IFA | EFFLUENT SUMMARY - EO/EG | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-SUM-004 | SUM | 4 | 8000-ZA-E-70034 | 0 | B | IFA | RELIEF LOAD SUMMARY - EO/EG | 2021-02-16 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8000 | A8RX-TSC-8000-225-SUM-005 | SUM | 5 | 8000-ZA-E-70031 | 0 | B | IFA | PROCESS SIZED EQUIPMENT SUMMARY - EO/EG | 2020-12-02 |  |  |  |  | PLH
A8RX-TEC/SAI | 250 | PIPING | 8000 | A8RX-TSC-8000-250-LAY-001 | LAY | 1 | 8000-GB-B-65120 | 0 | B | IFA | EO/MEG/DEG/TEG AREA - UNIT PLOT PLAN | 2020-11-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-RPT-201 | RPT | 201 | 8000-RA-E-22001 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR COLUMNS | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-RPT-202 | RPT | 202 | 8000-RA-E-22002 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR SHELL AND TUBE HEAT EXCHANGERS | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-RPT-203 | RPT | 203 | 8000-RA-E-22003 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR PLATE AND FRAME HEAT EXCHANGERS | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-RPT-204 | RPT | 204 | 8000-RA-E-22005 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR REACTORS | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-RPT-205 | RPT | 205 | 8000-RA-E-22006 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR INTERNALS FOR COLUMNS | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-SPC-201 | SPC | 201 | 8000-RA-E-20011 | 0 | B | IFA | SUPPLY SPECIFICATION FOR COLUMNS | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-SPC-202 | SPC | 202 | 8000-RA-E-20012 | 0 | B | IFA | SUPPLY SPECIFICATION FOR SHELL AND TUBE HEAT EXCHANGERS | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-SPC-203 | SPC | 203 | 8000-RA-E-20013 | 0 | B | IFA | SUPPLY SPECIFICATION FOR PLATE AND FRAME HEAT EXCHANGERS | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-SPC-204 | SPC | 204 | 8000-RA-E-20015 | 0 | B | IFA | SUPPLY SPECIFICATION FOR REACTORS | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-SPC-205 | SPC | 205 | 8000-RA-E-20016 | 0 | B | IFA | SUPPLY SPECIFICATION FOR INTERNALS FOR COLUMNS | 2020-12-08 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8000 | A8RX-TSC-8000-255-SPC-501 | SPC | 501 | 8000-MA-E-30003 | 0 | B | IFA | TECHNICAL SUPPLY SPECIFICATION FOR CENTRIFUGAL PUMPS ITEM G-8310/8311, G-8415/8416, G-8417/8418, G-8772/8773 | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8000 | A8RX-TSC-8000-255-STD-201 | STD | 201 | 8000-RA-E-20001 | 0 | B | IFA | STANDARD DRAWINGS FOR PRESSURE VESSELS AND HEAT EXCHANGERS | 2020-10-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8000 | A8RX-TSC-8000-255-SUM-501 | SUM | 501 | 8000-MA-E-30012 | 0 | B | IFA | EQUIPMENT SUMMARY FOR UNIT 8000 | 2020-12-09 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 8000 | A8RX-TSC-8000-265-LAY-001 | LAY | 1 | 8000-EB-A-40042 | 0 | B | IFA | ELECTRICAL AND INSTRUMENT EO/EG UNIT CABLE ROUTING | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 265 | ELECTRICAL | 8000 | A8RX-TSC-8000-265-SLD-001 | SLD | 1 | 8000-EC-B-40012 | 0 | B | IFA | KEY SINGLE LINE DIAGRAM EO/EG UNIT SUBSTATION | 2021-01-04 |  |  |  |  | PLH
A8RX-TEC/SAI | 270 | CONTROL SYSTEM & INSTRUMENTATION | 8000 | A8RX-TSC-8000-270-DTA-002 | DTA | 2 | 8000-SA-E-50011 | 0 | B | IFA | INSTRUMENT INDEX FOR EO/MEG/DEG/TEG - UNIT 8000 | 2020-12-29 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 8000 | A8RX-TSC-8000-653-DST-001 | DST | 1 | 8000-ZX-E-80012 | 0 | B | IFI | MSDS COMPILATION - EO/MEG/DEG/TEG UNIT | 2021-02-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 8000 | A8RX-TSC-8000-653-HAC-001 | HAC | 1 | 8000-ZB-B-85012 | 0 | B | IFA | HAZARDOUS AREA CLASSIFICATION LAYOUT - EO/MEG/DEG/TEG AREA | 2020-12-23 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 8000 | A8RX-TSC-8000-653-LAY-001 | LAY | 1 | 8000-ZB-B-85006 | 0 | B | IFA | FIRE AND GAS DETECTION LAYOUT - EO/MEG/DEG/TEG AREA | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 8000 | A8RX-TSC-8000-653-LAY-002 | LAY | 2 | 8000-ZB-B-85009 | 0 | B | IFA | FIREPROOFING ZONE LAYOUT - EO/MEG/DEG/TEG AREA | 2021-01-14 |  |  |  |  | PLH
A8RX-TEC/SAI | 653 | HSE | 8000 | A8RX-TSC-8000-653-LAY-003 | LAY | 3 | 8000-ZB-A-85021 | 0 | B | IFA | FIREWATER DISTRIBUTION LAYOUT - EO/MEG/DEG/TEG AREA | 2021-01-15 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-MSD-001 | MSD | 1 | 8100-GD-B-75200 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°1 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PFD-001 | PFD | 1 | 8100-GD-B-75000 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) - EO REACTION | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-001 | PID | 1 | 8100-GD-B-76000 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 1 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-002 | PID | 2 | 8100-GD-B-76001 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 2 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-003 | PID | 3 | 8100-GD-B-76002 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 3 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-004 | PID | 4 | 8100-GD-B-76003 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 4 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-005 | PID | 5 | 8100-GD-B-76004 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 5 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-006 | PID | 6 | 8100-GD-B-76005 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 6 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-007 | PID | 7 | 8100-GD-B-76006 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 7 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-008 | PID | 8 | 8100-GD-B-76007 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 8 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-009 | PID | 9 | 8100-GD-B-76008 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 9 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-010 | PID | 10 | 8100-GD-B-76009 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 10 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-011 | PID | 11 | 8100-GD-B-76010 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 11 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-012 | PID | 12 | 8100-GD-B-76011 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 12 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8100 | A8RX-TSC-8100-225-PID-013 | PID | 13 | 8100-GD-B-76012 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 13 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8100 | A8RX-TSC-8100-255-DST-201 | DST | 201 | 8100-RA-E-21006 | 0 | B | IFA | MECHANICAL DATASHEET FOR ETHYLENE OXIDE REACTOR ITEM E-8101 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8100 | A8RX-TSC-8100-255-DST-202 | DST | 202 | 8100-RA-E-21007 | 0 | B | IFA | MECHANICAL DATASHEET FOR CYCLE GAS / WATER EXCHANGER ITEM E-8104 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8100 | A8RX-TSC-8100-255-DST-203 | DST | 203 | 8100-RA-E-21008 | 0 | B | IFA | MECHANICAL DATASHEET FOR CYCLE GAS HEAT EXCHANGER ITEM E-8106 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8100 | A8RX-TSC-8100-255-DST-501 | DST | 501 | 8100-MA-E-31001 | 0 | B | IFA | MECHANICAL DATA SHEET FOR CENTRIFUGAL COMPRESSOR ITEM K-8116 | 2020-11-26 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8100 | A8RX-TSC-8100-255-RPT-501 | RPT | 501 | 8100-MA-E-32001 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR CENTRIFUGAL COMPRESSOR ITEM K-8116 | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8100 | A8RX-TSC-8100-255-SPC-501 | SPC | 501 | 8100-MA-E-30001 | 0 | B | IFA | TECHNICAL SUPPLY SPECIFICATION FOR CENTRIFUGAL COMPRESSOR ITEM K-8116 | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-MSD-001 | MSD | 1 | 8200-GD-B-75201 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°2 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PFD-001 | PFD | 1 | 8200-GD-B-75001 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) PURGE GLYCOL | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-001 | PID | 1 | 8200-GD-B-76022 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 23 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-002 | PID | 2 | 8200-GD-B-76021 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 22 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-003 | PID | 3 | 8200-GD-B-76020 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 21 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-004 | PID | 4 | 8200-GD-B-76019 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 20 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-005 | PID | 5 | 8200-GD-B-76018 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 19 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-006 | PID | 6 | 8200-GD-B-76017 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 18 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-007 | PID | 7 | 8200-GD-B-76016 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 17 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-008 | PID | 8 | 8200-GD-B-76015 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 16 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-009 | PID | 9 | 8200-GD-B-76014 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 15 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8200 | A8RX-TSC-8200-225-PID-010 | PID | 10 | 8200-GD-B-76013 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 14 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-MSD-001 | MSD | 1 | 8300-GD-B-75202 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°3 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PFD-001 | PFD | 1 | 8300-GD-B-75002 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) CO2 REMOVAL | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-001 | PID | 1 | 8300-GD-B-76023 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 24 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-002 | PID | 2 | 8300-GD-B-76024 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 25 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-003 | PID | 3 | 8300-GD-B-76025 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 26 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-004 | PID | 4 | 8300-GD-B-76026 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 27 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-005 | PID | 5 | 8300-GD-B-76027 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 28 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-006 | PID | 6 | 8300-GD-B-76028 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 29 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-007 | PID | 7 | 8300-GD-B-76029 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 30 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-008 | PID | 8 | 8300-GD-B-76030 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 31 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-009 | PID | 9 | 8300-GD-B-76031 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 32 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8300 | A8RX-TSC-8300-225-PID-010 | PID | 10 | 8300-GD-B-76032 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 33 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8300 | A8RX-TSC-8300-255-DST-201 | DST | 201 | 8300-RA-E-21001 | 0 | B | IFA | MECHANICAL DATASHEET FOR CO2 ABSORBER / QUENCH COLUMN ITEM C-8301 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8300 | A8RX-TSC-8300-255-DST-202 | DST | 202 | 8300-RA-E-21002 | 0 | B | IFA | MECHANICAL DATASHEET FOR CO2 REGENERATOR COLUMN AND RICH SOLUTION FLASH ITEM C-8305 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8300 | A8RX-TSC-8300-255-DST-203 | DST | 203 | 8300-RA-E-21009 | 0 | B | IFA | MECHANICAL DATASHEET FOR CO2 REGENERATOR REBOILER N ITEM E-8307 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8300 | A8RX-TSC-8300-255-DST-204 | DST | 204 | 8300-RA-E-21010 | 0 | B | IFA | MECHANICAL DATASHEET FOR LEAN/RICH CARBONATE SOLUTION HEAT EXCHANGER ITEM E-8319 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8300 | A8RX-TSC-8300-255-DST-501 | DST | 501 | 8300-MA-E-31003 | 0 | B | IFA | MECHANICAL DATA SHEET FOR PUMPS G-8310/8311 | 2020-11-26 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8300 | A8RX-TSC-8300-255-RPT-501 | RPT | 501 | 8300-MA-E-32003 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR CENTRIFUGAL PUMPS ITEM G-8310/8311 | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-MSD-001 | MSD | 1 | 8400-GD-B-75203 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°4 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PFD-001 | PFD | 1 | 8400-GD-B-75003 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) E/O RECOVERY-REFINING | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-001 | PID | 1 | 8400-GD-B-76053 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 54 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-002 | PID | 2 | 8400-GD-B-76052 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 53 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-003 | PID | 3 | 8400-GD-B-76051 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 52 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-004 | PID | 4 | 8400-GD-B-76050 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 51 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-005 | PID | 5 | 8400-GD-B-76049 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 50 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-006 | PID | 6 | 8400-GD-B-76048 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 49 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-007 | PID | 7 | 8400-GD-B-76047 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 48 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-008 | PID | 8 | 8400-GD-B-76046 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 47 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-009 | PID | 9 | 8400-GD-B-76045 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 46 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-010 | PID | 10 | 8400-GD-B-76044 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 45 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-011 | PID | 11 | 8400-GD-B-76043 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 44 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-012 | PID | 12 | 8400-GD-B-76042 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 43 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-013 | PID | 13 | 8400-GD-B-76041 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 42 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-014 | PID | 14 | 8400-GD-B-76040 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 41 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-015 | PID | 15 | 8400-GD-B-76039 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 40 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-016 | PID | 16 | 8400-GD-B-76038 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 39 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-017 | PID | 17 | 8400-GD-B-76037 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 38 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-018 | PID | 18 | 8400-GD-B-76036 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 37 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-019 | PID | 19 | 8400-GD-B-76035 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 36 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-020 | PID | 20 | 8400-GD-B-76034 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 35 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8400 | A8RX-TSC-8400-225-PID-021 | PID | 21 | 8400-GD-B-76033 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 34 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8400 | A8RX-TSC-8400-255-DST-201 | DST | 201 | 8400-RA-E-21003 | 0 | B | IFA | MECHANICAL DATASHEET FOR MAIN SCRUBBER ITEM C-8401 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8400 | A8RX-TSC-8400-255-DST-202 | DST | 202 | 8400-RA-E-21004 | 0 | B | IFA | MECHANICAL DATASHEET FOR EO STRIPPER / REABSORBER COLUMN ITEM C-8404 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8400 | A8RX-TSC-8400-255-DST-203 | DST | 203 | 8400-RA-E-21011 | 0 | B | IFA | MECHANICAL DATASHEET FOR EO STRIPPER / REABSORBER FEED PREHEATER ITEM E-8403 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8400 | A8RX-TSC-8400-255-DST-204 | DST | 204 | 8400-RA-E-21012 | 0 | B | IFA | MECHANICAL DATASHEET FOR EO STRIPPER / REABSORBER COLUMN INTERNAL CONDENSER ITEM E-8405 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8400 | A8RX-TSC-8400-255-DST-205 | DST | 205 | 8400-RA-E-21013 | 0 | B | IFA | MECHANICAL DATASHEET FOR EO STRIPPER / REABSORBER PRIMARY REBOILER ITEM E-8411 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8400 | A8RX-TSC-8400-255-DST-206 | DST | 206 | 8400-RA-E-21014 | 0 | B | IFA | MECHANICAL DATASHEET FOR SCRUBBER WATER COOLER ITEM E-8422 A/B/C | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8400 | A8RX-TSC-8400-255-DST-207 | DST | 207 | 8400-RA-E-21015 | 0 | B | IFA | MECHANICAL DATASHEET FOR REABSORBER WATER COOLER ITEM E-8446 A/B/C | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8400 | A8RX-TSC-8400-255-DST-208 | DST | 208 | 8400-RA-E-21016 | 0 | B | IFA | MECHANICAL DATASHEET FOR EO STRIPPER / REABSORBER TERTIARY REBOILER ITEM E-8495 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8400 | A8RX-TSC-8400-255-DST-209 | DST | 209 | 8400-RA-E-21017 | 0 | B | IFA | MECHANICAL DATASHEET FOR EO STRIPPER / REABSORBER SECONDARY REBOILER ITEM E-8485 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8400 | A8RX-TSC-8400-255-DST-501 | DST | 501 | 8400-MA-E-31002 | 0 | B | IFA | MECHANICAL DATA SHEET FOR RECIPROCATING COMPRESSOR ITEM K-8460 | 2020-11-26 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8400 | A8RX-TSC-8400-255-DST-502 | DST | 502 | 8400-MA-E-31004 | 0 | B | IFA | MECHANICAL DATA SHEET FOR PUMPS G-8415/8416 | 2020-11-26 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8400 | A8RX-TSC-8400-255-DST-503 | DST | 503 | 8400-MA-E-31005 | 0 | B | IFA | MECHANICAL DATA SHEET FOR PUMPS G-8417/8418 | 2020-11-26 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8400 | A8RX-TSC-8400-255-RPT-501 | RPT | 501 | 8400-MA-E-32002 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR CENTRIFUGAL COMPRESSOR ITEM K-8460 | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8400 | A8RX-TSC-8400-255-RPT-502 | RPT | 502 | 8400-MA-E-32004 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR CENTRIFUGAL PUMPS ITEM G-8415/8416 | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8400 | A8RX-TSC-8400-255-RPT-503 | RPT | 503 | 8400-MA-E-32005 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR CENTRIFUGAL PUMPS ITEM G-8417/8418 | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8400 | A8RX-TSC-8400-255-SPC-501 | SPC | 501 | 8400-MA-E-30002 | 0 | B | IFA | TECHNICAL SUPPLY SPECIFICATION FOR RECIPROCATING COMPRESSOR ITEM K-8460 | 2020-12-18 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8500 | A8RX-TSC-8500-225-PID-001 | PID | 1 | 8500-GD-B-76054 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 55 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8600 | A8RX-TSC-8600-225-MSD-002 | MSD | 2 | 8600-GD-B-75204 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°5 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8600 | A8RX-TSC-8600-225-PFD-001 | PFD | 1 | 8600-GD-B-75004 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8600 | A8RX-TSC-8600-225-PID-001 | PID | 1 | 8600-GD-B-76056 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 57 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8600 | A8RX-TSC-8600-225-PID-002 | PID | 2 | 8600-GD-B-76055 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 56 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-MSD-001 | MSD | 1 | 8700-GD-B-75205 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°6 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PFD-001 | PFD | 1 | 8700-GD-B-75005 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE GLYCOL REACTION AND EVAPORATION | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-001 | PID | 1 | 8700-GD-B-76074 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 75 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-002 | PID | 2 | 8700-GD-B-76073 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 74 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-003 | PID | 3 | 8700-GD-B-76072 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 73 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-004 | PID | 4 | 8700-GD-B-76071 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 72 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-005 | PID | 5 | 8700-GD-B-76070 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 71 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-006 | PID | 6 | 8700-GD-B-76069 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 70 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-007 | PID | 7 | 8700-GD-B-76068 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 69 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-008 | PID | 8 | 8700-GD-B-76067 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 68 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-009 | PID | 9 | 8700-GD-B-76066 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 67 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-010 | PID | 10 | 8700-GD-B-76065 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 66 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-011 | PID | 11 | 8700-GD-B-76064 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 65 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-012 | PID | 12 | 8700-GD-B-76063 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 64 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-013 | PID | 13 | 8700-GD-B-76062 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 63 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-014 | PID | 14 | 8700-GD-B-76061 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 62 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-015 | PID | 15 | 8700-GD-B-76060 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 61 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-016 | PID | 16 | 8700-GD-B-76059 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 60 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-017 | PID | 17 | 8700-GD-B-76058 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 59 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8700 | A8RX-TSC-8700-225-PID-018 | PID | 18 | 8700-GD-B-76057 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 58 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8700 | A8RX-TSC-8700-255-DST-501 | DST | 501 | 8700-MA-E-31006 | 0 | B | IFA | MECHANICAL DATA SHEET FOR PUMPS G-8772/8773 | 2020-11-26 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-MACHINERY | 8700 | A8RX-TSC-8700-255-RPT-501 | RPT | 501 | 8700-MA-E-32006 | 0 | B | IFI | TECHNICAL BID EVALUATION FOR CENTRIFUGAL PUMPS ITEM G-8772/8773 | 2021-02-22 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-MSD-001 | MSD | 1 | 8800-GD-B-75206 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°7 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PFD-001 | PFD | 1 | 8800-GD-B-75006 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) GLYCOL REFINING | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-001 | PID | 1 | 8800-GD-B-76075 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 76 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-002 | PID | 2 | 8800-GD-B-76076 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 77 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-003 | PID | 3 | 8800-GD-B-76077 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 78 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-004 | PID | 4 | 8800-GD-B-76078 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 79 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-005 | PID | 5 | 8800-GD-B-76079 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 80 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-006 | PID | 6 | 8800-GD-B-76080 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 81 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-007 | PID | 7 | 8800-GD-B-76081 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 82 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-008 | PID | 8 | 8800-GD-B-76082 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 83 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-009 | PID | 9 | 8800-GD-B-76083 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 84 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-010 | PID | 10 | 8800-GD-B-76084 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 85 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-011 | PID | 11 | 8800-GD-B-76085 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 86 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8800 | A8RX-TSC-8800-225-PID-012 | PID | 12 | 8800-GD-B-76086 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 87 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 255 | MECHANICAL-PVHE | 8800 | A8RX-TSC-8800-255-DST-201 | DST | 201 | 8800-RA-E-21005 | 0 | B | IFA | MECHANICAL DATASHEET FOR MEG REFINING COLUMN ITEM C-8821 | 2020-12-03 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-MSD-001 | MSD | 1 | 8900-GD-B-75208 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°9 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-MSD-002 | MSD | 2 | 8900-GD-B-75207 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°8 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-MSD-003 | MSD | 3 | 8900-GD-B-75212 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°13 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-MSD-004 | MSD | 4 | 8900-GD-B-75211 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°12 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-MSD-005 | MSD | 5 | 8900-GD-B-75210 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°11 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-MSD-006 | MSD | 6 | 8900-GD-B-75209 | 0 | B | IFA | MATERIAL SELECTION DIAGRAM - (ETHYLENE OXIDE) N°10 | 2020-10-27 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PFD-001 | PFD | 1 | 8900-GD-B-75008 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) N°9 | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PFD-002 | PFD | 2 | 8900-GD-B-75007 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) N°8 | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PFD-003 | PFD | 3 | 8900-GD-B-75012 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) N°13 | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PFD-004 | PFD | 4 | 8900-GD-B-75011 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) N°12 | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PFD-005 | PFD | 5 | 8900-GD-B-75010 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) N°11 | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PFD-006 | PFD | 6 | 8900-GD-B-75009 | 0 | B | IFA | PROCESS FLOW DIAGRAM (ETHYLENE OXIDE) N°10 | 2020-10-13 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-001 | PID | 1 | 8900-GD-B-76205 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE DISTRIBUTION WATERS | 2020-11-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-002 | PID | 2 | 8900-GD-B-76201 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE DISTRIBUTION STEAM | 2020-11-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-003 | PID | 3 | 8900-GD-B-76200 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE DISTRIBUTION NITROGEN AND IA/UA | 2020-11-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-004 | PID | 4 | 8900-GD-B-76204 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE DISTRIBUTION FLARE | 2020-11-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-005 | PID | 5 | 8900-GD-B-76203 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE DISTRIBUTION COOLING WATER | 2020-11-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-006 | PID | 6 | 8900-GD-B-76202 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE DISTRIBUTION CONDENSATE | 2020-11-25 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-007 | PID | 7 | 8900-GD-B-76091 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 92 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-008 | PID | 8 | 8900-GD-B-76090 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 91 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-009 | PID | 9 | 8900-GD-B-76089 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 90 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-010 | PID | 10 | 8900-GD-B-76088 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 89 | 2020-11-10 |  |  |  |  | PLH
A8RX-TEC/SAI | 225 | PROCESS | 8900 | A8RX-TSC-8900-225-PID-011 | PID | 11 | 8900-GD-B-76087 | 0 | B | IFA | PROCESS PID ETHYLENE OXIDE (TITLE + LICENSOR DWG NUMBER) N° 88 | 2020-11-10 |  |  |  |  | PLH